## README
PDI Dashboard - Backend Data Workbook
Purpose | Single source of truth feeding the Power BI Desktop report and the Excel-native views of the Engineering & Projects Portfolio Hub.
As-of date | All 'current' figures in this dummy dataset (progress %, overdue flags, KPI snapshots) are calculated as of the date in Config!B2, not TODAY(). Change that one cell to move the whole dataset's story forward.
Folder links | Set Config!B3 to your OneDrive 'Project Files' parent folder URL once. Every project's FolderLink column then builds automatically from Config!B3 + Projects!FolderName (see Projects sheet).
Data volume | Data is fully populated/realistic dummy data across 31 tracked projects (24 active + 7 closeout), 52 people, 400+ deliverables, 30+ risks, 100+ milestones and schedule activities, and a 12-month S-curve per active project. Six projects (PRJ-024, PRJ-021, PRJ-018, PRJ-015, PRJ-011, GLB-003) and their headline numbers are taken verbatim from the original HTML mockup; everything else is realistic invented data generated for a working demo, and totals will not match the mockup's placeholder KPI numbers to the digit since those were never wired to real records.
Sheet | What it is
Config | Two settings you edit: AsOfDate and OneDriveBaseURL.
Lookups | Dropdown/reference lists used for data validation and Power BI slicers.
Projects | Master project register - one row per tracked project. Everything else hangs off ProjectID.
People | Division headcount (engineering disciplines + PM/Services/CRV).
Allocations | Bridge table: who is working on which project, at what %.
Deliverables | Master Deliverables Register (MDR) - one row per document/deliverable.
Risks | Risk register (RAID log).
Issues | Open issues (RAID log).
Actions | Open actions (RAID log).
ChangeRequests | Change requests (RAID log).
Milestones | Key dates and gate reviews per project.
Schedule_Activities | Gantt bar data per active project (activity, start date, end date, % complete).
SCurve_Monthly | Monthly planned vs actual progress % per active project - drives every S-curve chart.
Build order | This workbook is fully populated end-to-end, but the Power BI report is being built in phases: Phase 1 = Home + Active Projects (portfolio) pages. Later phases wire up Project 360, Deliverables/MDR, Schedule & Controls, Resources and Risks pages using tables already in this workbook.

## Config
Setting | Value
AsOfDate | 2026-08-15
OneDriveBaseURL | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE

## Lookups
Departments | Disciplines | Assets | DeliveryModels | StageGates | HealthStatus | RegisterStatus | WorkflowStatus | RiskCategory | ProjectType
Engineering | Process | OML 1 | In-house | Identify | Green | Active | Internal Development | Schedule | Asset Project
Project Services | Mechanical | OML 2 | In-house -> Contractor | Assess | Amber | Closeout | Issued for Review | Cost | Global Initiative
Project Execution | Piping | OML 3 | Contractor-led | Select | Red |  | Comments Received | Execution
CRV | Instrumentation | OML 4 | Hybrid | Define |  |  | Revise & Resubmit | Technical
| Electrical | OML 5 |  | Execute |  |  | Approved / IFI | Safety
| Civil / Structural | OML 6 |  | Operate |  |  |  | Commercial
| Pipeline | OML 7
| Project Engineering | OML 8
OML 9
OML 10
Global

## Projects
ProjectID | ProjectName | ShortDescription | Asset | Department | DeliveryModel | ProjectType | StageGate | PortfolioPhase | RegisterStatus | ProjectManager | LeadEngineer | PlannedProgressPct | ActualProgressPct | ScheduleVarianceDays | HealthStatus | StartDate | PlannedCompletionDate | ForecastCompletionDate | DeliverablesTotal | DeliverablesComplete | DeliverablesOverdue | OpenRisksCount | ResourceHeadcount | MDRClosedPct | PunchItems | LessonsLearnedStatus | ScopeDescription | FolderName | FolderLink | FolderURL
PRJ-024 | North Hub Compression Upgrade | Compression upgrade | OML 4 | Engineering | In-house -> Contractor | Asset Project | Define | Define | Active | O. Adeyemi | A. Musa | 72 | 68 | 6 | Amber | 2025-10-15 | 2026-08-29 | 2026-09-04 | 22 | 18 | 1 | 4 | 6 | 82 | 0 | Pending | Upgrade of the existing compression train to increase gas handling capacity and improve operating reliability. Scope includes process simulation, equipment selection, piping modification, E&I design and execution support. | PRJ-024 - North Hub Compression Upgrade | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-024 - North Hub Compression Upgrade
PRJ-021 | Offshore Water Injection | Brownfield modification | OML 7 | Project Execution | Hybrid | Asset Project | Execute | Execute | Active | T. Ibrahim | F. Etim | 75 | 74 | -2 | Green | 2025-05-10 | 2026-11-10 | 2026-11-06 | 22 | 14 | 1 | 1 | 6 | 64 | 0 | Pending | Brownfield modification of the offshore water injection system to restore injection capacity and support reservoir pressure maintenance. | PRJ-021 - Offshore Water Injection | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-021 - Offshore Water Injection
PRJ-018 | Produced Water Upgrade | Process debottlenecking | OML 2 | Engineering | In-house | Asset Project | Assess | Concept / Assess | Active | A. Okoro | G. Chukwu | 43 | 37 | 0 | Green | 2026-06-20 | 2027-02-20 | 2027-02-20 | 19 | 9 | 2 | 2 | 5 | 47 | 0 | Pending | Process debottlenecking of the produced water treatment train to meet revised discharge and reinjection specifications. | PRJ-018 - Produced Water Upgrade | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-018 - Produced Water Upgrade
PRJ-015 | Gas Export Metering | Metering package | OML 10 | Engineering | Contractor-led | Asset Project | Define | Define | Active | M. Bello | S. Aliyu | 58 | 52 | 12 | Red | 2025-09-15 | 2026-10-15 | 2026-11-01 | 18 | 11 | 3 | 1 | 2 | 61 | 0 | Pending | Replacement metering package for gas export fiscal measurement, including new metering skid, prover loop and control system integration. | PRJ-015 - Gas Export Metering | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-015 - Gas Export Metering
PRJ-011 | Utilities Reliability | Utilities upgrade | OML 1 | Project Execution | In-house | Asset Project | Execute | Execute | Active | R. Bello | D. Umeh | 84 | 86 | -2 | Green | 2025-06-18 | 2026-09-18 | 2026-09-16 | 17 | 16 | 0 | 0 | 0 | 94 | 0 | Pending | Reliability improvement programme across instrument air, power generation and cooling water utility systems. | PRJ-011 - Utilities Reliability | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-011 - Utilities Reliability
GLB-003 | Licence Validation Programme | Cross-asset licence compliance | Global | CRV | In-house | Global Initiative | Assess | Concept / Assess | Active | K. Briggs | H. Sanni | 45 | 43 | 0 | Amber | 2026-06-01 | 2027-03-01 | 2027-03-15 | 20 | 7 | 2 | 0 | 1 | 35 | 0 | Pending | Cross-asset programme validating licence-to-operate documentation and regulatory compliance evidence across all producing assets. | GLB-003 - Licence Validation Programme | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/GLB-003 - Licence Validation Programme
PRJ-006 | Utility Tie-In | Utility interconnection | OML 1 | Project Execution | In-house | Asset Project | Operate | Closeout / Archive | Closeout | R. Bello | D. Umeh | 100 | 100 | 0 | Amber | 2025-01-30 | 2026-06-30 | 2026-07-05 | 16 | 15 | 0 | 0 | 0 | 94 | 3 | Pending | Tie-in of new utility interconnection between the central processing facility and satellite flowstation. | PRJ-006 - Utility Tie-In | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-006 - Utility Tie-In
PRJ-009 | Compressor Reliability | Reliability upgrade | OML 4 | Engineering | In-house | Asset Project | Operate | Closeout / Archive | Closeout | O. Adeyemi | A. Musa | 100 | 100 | 0 | Green | 2024-09-20 | 2026-05-20 | 2026-05-18 | 19 | 18 | 0 | 0 | 0 | 95 | 0 | Complete | Reliability upgrade of export compressor auxiliaries following repeated trip events. | PRJ-009 - Compressor Reliability | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-009 - Compressor Reliability
PRJ-005 | Separator Debottleneck Study | Concept study | OML 3 | Engineering | In-house | Asset Project | Assess | Concept / Assess | Active | F. Nwosu | I. Ogundele | 32 | 28 | 3 | Green | 2026-04-10 | 2027-01-10 | 2027-01-15 | 11 | 3 | 4 | 1 | 3 | 27 | 0 | Pending | Concept-level study to debottleneck the second-stage separator train ahead of planned production ramp-up. | PRJ-005 - Separator Debottleneck Study | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-005 - Separator Debottleneck Study
PRJ-008 | Flare System Upgrade | Concept study | OML 4 | Engineering | In-house | Asset Project | Assess | Concept / Assess | Active | N. Balogun | A. Musa | 28 | 22 | 5 | Amber | 2026-05-05 | 2027-02-05 | 2027-02-14 | 13 | 2 | 3 | 1 | 3 | 15 | 0 | Pending | Assessment of flare tip and knockout drum capacity against revised process design basis. | PRJ-008 - Flare System Upgrade | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-008 - Flare System Upgrade
PRJ-013 | Wellhead Platform Modification | Concept select | OML 5 | Engineering | Hybrid | Asset Project | Select | Concept / Assess | Active | C. Danjuma | T. Ogundele | 40 | 36 | 4 | Green | 2026-04-20 | 2026-12-20 | 2026-12-28 | 16 | 4 | 2 | 0 | 6 | 25 | 0 | Pending | Selection of preferred concept for wellhead platform modification to accommodate two additional well slots. | PRJ-013 - Wellhead Platform Modification | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-013 - Wellhead Platform Modification
PRJ-019 | Corrosion Management Programme | Identify | OML 7 | Engineering | In-house | Asset Project | Identify | Concept / Assess | Active | L. Abubakar | F. Etim | 14 | 11 | 2 | Green | 2026-12-01 | 2027-04-01 | 2027-04-08 | 8 | 1 | 1 | 1 | 1 | 13 | 0 | Pending | Identification phase for an integrity programme addressing internal corrosion on ageing flowline network. | PRJ-019 - Corrosion Management Programme | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-019 - Corrosion Management Programme
PRJ-023 | Digital Field Monitoring | Concept study | OML 10 | Engineering | In-house | Global Initiative | Assess | Concept / Assess | Active | S. Aliyu | M. Ekong | 30 | 24 | 6 | Amber | 2026-06-25 | 2027-01-25 | 2027-02-05 | 13 | 3 | 2 | 4 | 2 | 23 | 0 | Pending | Assessment of digital field monitoring and remote surveillance options for the metering and wellhead network. | PRJ-023 - Digital Field Monitoring | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-023 - Digital Field Monitoring
GLB-004 | HSE Case Revalidation | Cross-asset select | Global | CRV | In-house | Global Initiative | Select | Concept / Assess | Active | K. Briggs | H. Sanni | 38 | 35 | 3 | Green | 2026-03-10 | 2026-12-10 | 2026-12-16 | 13 | 5 | 1 | 0 | 0 | 38 | 0 | Pending | Cross-asset programme to revalidate HSE cases against updated regulatory guidance and incident learnings. | GLB-004 - HSE Case Revalidation | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/GLB-004 - HSE Case Revalidation
PRJ-001 | Wellhead Flowline Replacement | FEED | OML 1 | Engineering | Contractor-led | Asset Project | Define | Define | Active | R. Bello | D. Umeh | 58 | 51 | 5 | Amber | 2026-02-20 | 2026-11-20 | 2026-11-30 | 22 | 10 | 3 | 0 | 3 | 45 | 0 | Pending | FEED for replacement of ageing wellhead flowlines identified through the corrosion inspection programme. | PRJ-001 - Wellhead Flowline Replacement | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-001 - Wellhead Flowline Replacement
PRJ-003 | Chemical Injection Upgrade | FEED | OML 2 | Engineering | In-house | Asset Project | Define | Define | Active | A. Okoro | G. Chukwu | 62 | 57 | 3 | Green | 2025-10-30 | 2026-10-30 | 2026-11-05 | 16 | 10 | 1 | 2 | 2 | 63 | 0 | Pending | Front-end design for upgraded chemical injection skids to support produced water treatment performance. | PRJ-003 - Chemical Injection Upgrade | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-003 - Chemical Injection Upgrade
PRJ-007 | Compressor Train Automation | FEED | OML 4 | Engineering | Hybrid | Asset Project | Define | Define | Active | O. Adeyemi | A. Musa | 55 | 47 | 8 | Amber | 2025-11-05 | 2026-12-05 | 2026-12-20 | 22 | 10 | 2 | 0 | 3 | 45 | 0 | Pending | Design of upgraded automation and anti-surge control for the compression train serving OML 4. | PRJ-007 - Compressor Train Automation | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-007 - Compressor Train Automation
PRJ-010 | Produced Water Reinjection | FEED | OML 5 | Engineering | In-house | Asset Project | Define | Define | Active | C. Danjuma | T. Ogundele | 50 | 44 | 6 | Amber | 2026-01-15 | 2027-01-15 | 2027-01-28 | 20 | 10 | 0 | 1 | 5 | 50 | 0 | Pending | Front-end design for produced water reinjection facilities to reduce surface discharge volumes. | PRJ-010 - Produced Water Reinjection | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-010 - Produced Water Reinjection
PRJ-014 | Power Generation Upgrade | FEED | OML 6 | Engineering | Contractor-led | Asset Project | Define | Define | Active | J. Adamu | M. Ekong | 63 | 60 | 2 | Green | 2025-09-08 | 2026-10-08 | 2026-10-10 | 17 | 11 | 0 | 0 | 1 | 65 | 0 | Pending | Front-end design for additional gas turbine generation capacity to meet forecast facility power demand. | PRJ-014 - Power Generation Upgrade | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-014 - Power Generation Upgrade
PRJ-020 | SCADA Modernisation | FEED | OML 8 | Engineering | In-house | Asset Project | Define | Define | Active | B. Yakubu | H. Sanni | 46 | 40 | 7 | Amber | 2026-02-12 | 2027-02-12 | 2027-02-25 | 20 | 8 | 0 | 3 | 6 | 40 | 0 | Pending | Modernisation of the field SCADA and telemetry system connecting wellheads to the central control room. | PRJ-020 - SCADA Modernisation | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-020 - SCADA Modernisation
GLB-005 | Pipeline Integrity Digitalisation | FEED | Global | CRV | In-house | Global Initiative | Define | Define | Active | K. Briggs | H. Sanni | 49 | 45 | 4 | Green | 2026-02-05 | 2027-01-05 | 2027-01-12 | 22 | 10 | 0 | 3 | 2 | 45 | 0 | Pending | Cross-asset digitalisation of pipeline integrity inspection records into a single management system. | GLB-005 - Pipeline Integrity Digitalisation | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/GLB-005 - Pipeline Integrity Digitalisation
PRJ-004 | Fire and Gas System Renewal | Construction | OML 1 | Project Execution | Contractor-led | Asset Project | Execute | Execute | Active | R. Bello | D. Umeh | 80 | 76 | 4 | Amber | 2025-04-25 | 2026-09-25 | 2026-10-02 | 21 | 16 | 0 | 1 | 3 | 76 | 0 | Pending | Renewal of the fire and gas detection system across the central processing facility. | PRJ-004 - Fire and Gas System Renewal | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-004 - Fire and Gas System Renewal
PRJ-012 | Compressor Overhaul | Construction | OML 4 | Project Execution | In-house | Asset Project | Execute | Execute | Active | O. Adeyemi | A. Musa | 88 | 91 | -3 | Green | 2025-02-05 | 2026-09-05 | 2026-09-02 | 26 | 23 | 0 | 1 | 3 | 88 | 0 | Pending | Major overhaul of the standby export compressor, including rotor replacement and control system upgrade. | PRJ-012 - Compressor Overhaul | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-012 - Compressor Overhaul
PRJ-016 | Subsea Tie-in Campaign | Construction | OML 7 | Project Execution | Contractor-led | Asset Project | Execute | Execute | Active | T. Ibrahim | F. Etim | 70 | 65 | 6 | Amber | 2025-09-28 | 2026-11-28 | 2026-12-08 | 21 | 13 | 0 | 1 | 2 | 62 | 0 | Pending | Subsea tie-in campaign connecting two new well slots into the existing manifold and riser system. | PRJ-016 - Subsea Tie-in Campaign | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-016 - Subsea Tie-in Campaign
PRJ-022 | Electrical Substation Upgrade | Construction | OML 9 | Project Execution | Hybrid | Asset Project | Execute | Execute | Active | J. Adamu | M. Ekong | 76 | 71 | 5 | Amber | 2025-06-20 | 2026-10-20 | 2026-10-30 | 21 | 16 | 0 | 1 | 5 | 76 | 0 | Pending | Upgrade of the 33kV substation supplying the flowstation to accommodate additional electrical load. | PRJ-022 - Electrical Substation Upgrade | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-022 - Electrical Substation Upgrade
PRJ-026 | Tank Farm Expansion | Construction | OML 10 | Project Execution | Contractor-led | Asset Project | Execute | Execute | Active | M. Bello | S. Aliyu | 82 | 79 | 3 | Green | 2025-05-30 | 2026-09-30 | 2026-10-05 | 17 | 14 | 0 | 0 | 2 | 82 | 0 | Pending | Expansion of crude storage capacity through addition of two new floating-roof tanks. | PRJ-026 - Tank Farm Expansion | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-026 - Tank Farm Expansion
PRJ-017 | Wellhead Platform Refurbishment | Closeout | OML 7 | Project Execution | In-house | Asset Project | Operate | Closeout / Archive | Closeout | T. Ibrahim | F. Etim | 100 | 100 | 0 | Green | 2024-12-15 | 2026-07-15 | 2026-07-12 | 17 | 17 | 0 | 0 | 0 | 100 | 1 | Complete | Refurbishment of ageing wellhead platform structure and piping, now in closeout. | PRJ-017 - Wellhead Platform Refurbishment | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-017 - Wellhead Platform Refurbishment
PRJ-027 | Instrument Air System Replacement | Closeout | OML 2 | Project Execution | In-house | Asset Project | Operate | Closeout / Archive | Closeout | A. Okoro | G. Chukwu | 100 | 100 | 0 | Amber | 2024-12-10 | 2026-06-10 | 2026-06-20 | 21 | 20 | 0 | 0 | 0 | 95 | 5 | Pending | Replacement of the instrument air compressors and dryers, now in closeout. | PRJ-027 - Instrument Air System Replacement | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-027 - Instrument Air System Replacement
PRJ-028 | Metering Skid Replacement | Closeout | OML 10 | Project Execution | Contractor-led | Asset Project | Operate | Closeout / Archive | Closeout | M. Bello | S. Aliyu | 100 | 100 | 0 | Green | 2024-09-28 | 2026-05-28 | 2026-05-25 | 16 | 16 | 0 | 0 | 0 | 100 | 0 | Complete | Replacement of the custody transfer metering skid, now in closeout. | PRJ-028 - Metering Skid Replacement | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/PRJ-028 - Metering Skid Replacement
GLB-001 | Regional Pipeline ROW Survey | Closeout | Global | CRV | In-house | Global Initiative | Operate | Closeout / Archive | Closeout | K. Briggs | H. Sanni | 100 | 100 | 0 | Green | 2025-02-28 | 2026-04-30 | 2026-04-28 | 17 | 17 | 0 | 0 | 0 | 100 | 0 | Complete | Cross-asset right-of-way survey and encroachment programme, now in closeout. | GLB-001 - Regional Pipeline ROW Survey | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/GLB-001 - Regional Pipeline ROW Survey
GLB-002 | Emergency Response Plan Update | Closeout | Global | CRV | In-house | Global Initiative | Operate | Closeout / Archive | Closeout | K. Briggs | H. Sanni | 100 | 100 | 0 | Amber | 2024-11-20 | 2026-03-20 | 2026-03-25 | 19 | 18 | 0 | 0 | 0 | 95 | 2 | Pending | Cross-asset update of emergency response plans and drills, pending final sign-off. | GLB-002 - Emergency Response Plan Update | Open project folder | PASTE-YOUR-ONEDRIVE-PROJECT-FILES-FOLDER-URL-HERE/GLB-002 - Emergency Response Plan Update

## People
PersonID | Name | Discipline | Department | CapacityFTE | PrimaryAsset | AllocatedPct | UtilisationStatus
P-001 | A. Musa | Process | Engineering | 1 | OML 4 | 84 | Healthy
P-002 | G. Chukwu | Process | Engineering | 1 | OML 2 | 106 | Overloaded
P-003 | S. Aliyu | Process | Engineering | 1 | OML 10 | 112 | Overloaded
P-004 | D. Umeh | Mechanical | Engineering | 1 | OML 1 | 113 | Overloaded
P-005 | B. Yusuf | Mechanical | Engineering | 1 | OML 4 | 63 | Available
P-006 | B. Okafor | Mechanical | Engineering | 1 | OML 4 | 96 | High
P-007 | I. Ogundele | Piping | Engineering | 1 | OML 3 | 59 | Available
P-008 | E. Okoro | Piping | Engineering | 1 | OML 2 | 61 | Available
P-009 | H. Sanni | Instrumentation | Engineering | 1 | Global | 50 | Available
P-010 | F. Etim | Electrical | Engineering | 1 | OML 7 | 51 | Available
P-011 | M. Ekong | Electrical | Engineering | 1 | OML 9 | 47 | Available
P-012 | C. James | Electrical | Engineering | 1 | OML 7 | 112 | Overloaded
P-013 | T. Ogundele | Civil / Structural | Engineering | 1 | OML 5 | 95 | High
P-014 | I. Briggs | Instrumentation | Engineering | 1 | OML 1 | 100 | High
P-015 | S. Uzoma | Instrumentation | Engineering | 1 | OML 4 | 88 | Healthy
P-016 | S. Aliyu | Instrumentation | Engineering | 1 | OML 8 | 70 | Healthy
P-017 | Q. Chukwu | Mechanical | Engineering | 1 | OML 2 | 92 | Healthy
P-018 | A. Ihejirika | Mechanical | Engineering | 1 | OML 7 | 89 | Healthy
P-019 | J. Ibrahim | Process | Engineering | 1 | OML 5 | 76 | Healthy
P-020 | J. Musa | Process | Engineering | 1 | Global | 96 | High
P-021 | N. Effiong | Process | Engineering | 1 | OML 4 | 92 | Healthy
P-022 | E. Danjuma | Piping | Engineering | 1 | OML 9 | 102 | High
P-023 | U. Chukwuemeka | Piping | Engineering | 1 | OML 9 | 101 | High
P-024 | P. Ndukwe | Piping | Engineering | 1 | OML 5 | 83 | Healthy
P-025 | N. Uzoma | Civil / Structural | Engineering | 1 | OML 4 | 74 | Healthy
P-026 | M. Yakubu | Civil / Structural | Engineering | 1 | OML 8 | 79 | Healthy
P-027 | O. Musa | Project Engineering | Engineering | 1 | OML 6 | 100 | High
P-028 | H. Sanni | Project Engineering | Engineering | 1 | OML 4 | 77 | Healthy
P-029 | C. Ihejirika | Project Engineering | Engineering | 1 | OML 8 | 72 | Healthy
P-030 | R. Balogun | Pipeline | Engineering | 1 | OML 8 | 89 | Healthy
P-031 | C. Ibrahim | Pipeline | Engineering | 1 | OML 3 | 103 | High
P-032 | R. Ogunleye | Electrical | Engineering | 1 | OML 7 | 71 | Healthy
P-033 | O. Adeyemi | Project Management | Project Execution | 1 | OML 4 | 92 | Healthy
P-034 | T. Ibrahim | Project Management | Project Execution | 1 | OML 7 | 83 | Healthy
P-035 | A. Okoro | Project Management | Project Execution | 1 | OML 2 | 73 | Healthy
P-036 | M. Bello | Project Management | Project Execution | 1 | OML 10 | 88 | Healthy
P-037 | R. Bello | Project Management | Project Execution | 1 | OML 1 | 80 | Healthy
P-038 | K. Briggs | Project Management | CRV | 1 | Global | 85 | Healthy
P-039 | F. Nwosu | Project Management | Project Execution | 1 | OML 3 | 87 | Healthy
P-040 | N. Balogun | Project Management | Project Execution | 1 | OML 4 | 78 | Healthy
P-041 | C. Danjuma | Project Management | Project Execution | 1 | OML 5 | 78 | Healthy
P-042 | L. Abubakar | Project Management | Project Execution | 1 | OML 7 | 98 | High
P-043 | J. Adamu | Project Management | Project Execution | 1 | OML 9 | 88 | Healthy
P-044 | B. Yakubu | Project Management | Project Execution | 1 | OML 8 | 98 | High
P-045 | I. James | Community / Regulatory | CRV | 1 | OML 5 | 83 | Healthy
P-046 | L. Okafor | Project Controls | Project Services | 1 | OML 5 | 97 | High
P-047 | I. Okoro | Project Controls | Project Services | 1 | OML 4 | 85 | Healthy
P-048 | F. Eze | Project Controls | Project Services | 1 | OML 8 | 82 | Healthy
P-049 | H. Musa | Project Controls | Project Services | 1 | OML 10 | 94 | Healthy
P-050 | M. Mohammed | Project Controls | Project Services | 1 | OML 5 | 74 | Healthy
P-051 | R. Nwosu | Project Controls | Project Services | 1 | OML 9 | 78 | Healthy
P-052 | H. Yusuf | Project Controls | Project Services | 1 | OML 1 | 95 | High

## Allocations
AllocationID | PersonID | ProjectID | AllocationPct | RoleOnProject
AL-001 | P-012 | PRJ-021 | 65 | Electrical Engineer
AL-002 | P-012 | PRJ-024 | 47 | Electrical Engineer
AL-003 | P-006 | PRJ-024 | 55 | Mechanical Engineer
AL-004 | P-006 | PRJ-018 | 41 | Mechanical Engineer
AL-005 | P-001 | PRJ-024 | 50 | Lead Process Engineer
AL-006 | P-001 | PRJ-015 | 34 | Process Engineer
AL-007 | P-008 | PRJ-018 | 61 | Piping Engineer
AL-008 | P-002 | PRJ-003 | 65 | Process Engineer
AL-009 | P-002 | PRJ-018 | 41 | Process Engineer
AL-010 | P-003 | PRJ-023 | 72 | Process Engineer
AL-011 | P-003 | PRJ-026 | 40 | Process Engineer
AL-012 | P-004 | PRJ-001 | 113 | Mechanical Engineer
AL-013 | P-005 | PRJ-024 | 63 | Mechanical Engineer
AL-014 | P-007 | PRJ-005 | 59 | Piping Engineer
AL-015 | P-009 | GLB-005 | 50 | Instrumentation Engineer
AL-016 | P-010 | PRJ-019 | 24 | Electrical Engineer
AL-017 | P-010 | PRJ-021 | 27 | Electrical Engineer
AL-018 | P-011 | PRJ-022 | 47 | Electrical Engineer
AL-019 | P-013 | PRJ-013 | 46 | Civil / Structural Engineer
AL-020 | P-013 | PRJ-010 | 49 | Civil / Structural Engineer
AL-021 | P-014 | PRJ-004 | 48 | Instrumentation Engineer
AL-022 | P-014 | PRJ-001 | 52 | Instrumentation Engineer
AL-023 | P-015 | PRJ-012 | 54 | Instrumentation Engineer
AL-024 | P-015 | PRJ-008 | 34 | Instrumentation Engineer
AL-025 | P-016 | PRJ-020 | 70 | Instrumentation Engineer
AL-026 | P-017 | PRJ-018 | 48 | Mechanical Engineer
AL-027 | P-017 | PRJ-003 | 44 | Mechanical Engineer
AL-028 | P-018 | PRJ-021 | 89 | Mechanical Engineer
AL-029 | P-019 | PRJ-010 | 40 | Process Engineer
AL-030 | P-019 | PRJ-013 | 36 | Process Engineer
AL-031 | P-020 | GLB-003 | 96 | Process Engineer
AL-032 | P-021 | PRJ-007 | 47 | Process Engineer
AL-033 | P-021 | PRJ-024 | 45 | Process Engineer
AL-034 | P-022 | PRJ-022 | 102 | Piping Engineer
AL-035 | P-023 | PRJ-022 | 101 | Piping Engineer
AL-036 | P-024 | PRJ-010 | 47 | Piping Engineer
AL-037 | P-024 | PRJ-013 | 36 | Piping Engineer
AL-038 | P-025 | PRJ-008 | 74 | Civil / Structural Engineer
AL-039 | P-026 | PRJ-020 | 79 | Civil / Structural Engineer
AL-040 | P-027 | PRJ-014 | 100 | Project Engineering Engineer
AL-041 | P-028 | PRJ-008 | 35 | Project Engineering Engineer
AL-042 | P-028 | PRJ-007 | 42 | Project Engineering Engineer
AL-043 | P-029 | PRJ-020 | 72 | Project Engineering Engineer
AL-044 | P-030 | PRJ-020 | 89 | Pipeline Engineer
AL-045 | P-031 | PRJ-005 | 103 | Pipeline Engineer
AL-046 | P-032 | PRJ-021 | 71 | Electrical Engineer
AL-047 | P-033 | PRJ-024 | 57 | Project Manager
AL-048 | P-033 | PRJ-007 | 35 | Project Manager
AL-049 | P-034 | PRJ-021 | 51 | Project Manager
AL-050 | P-034 | PRJ-016 | 32 | Project Manager
AL-051 | P-035 | PRJ-018 | 73 | Project Manager
AL-052 | P-036 | PRJ-015 | 88 | Project Manager
AL-053 | P-037 | PRJ-004 | 80 | Project Manager
AL-054 | P-038 | GLB-005 | 85 | Project Manager
AL-055 | P-039 | PRJ-005 | 87 | Project Manager
AL-056 | P-040 | PRJ-012 | 78 | Project Manager
AL-057 | P-041 | PRJ-010 | 37 | Project Manager
AL-058 | P-041 | PRJ-013 | 41 | Project Manager
AL-059 | P-042 | PRJ-016 | 56 | Project Manager
AL-060 | P-042 | PRJ-021 | 42 | Project Manager
AL-061 | P-043 | PRJ-022 | 88 | Project Manager
AL-062 | P-044 | PRJ-020 | 98 | Project Manager
AL-063 | P-045 | PRJ-013 | 83 | CRV Coordinator
AL-064 | P-046 | PRJ-013 | 97 | Project Controls Lead
AL-065 | P-047 | PRJ-012 | 85 | Project Controls Lead
AL-066 | P-048 | PRJ-020 | 82 | Project Controls Lead
AL-067 | P-049 | PRJ-023 | 51 | Project Controls Lead
AL-068 | P-049 | PRJ-026 | 43 | Project Controls Lead
AL-069 | P-050 | PRJ-010 | 74 | Project Controls Lead
AL-070 | P-051 | PRJ-022 | 78 | Project Controls Lead
AL-071 | P-052 | PRJ-001 | 48 | Project Controls Lead
AL-072 | P-052 | PRJ-004 | 47 | Project Controls Lead

## Deliverables
DeliverableID | ProjectID | DeliverableName | Discipline | ResponsiblePerson | Revision | IssueDate | DueDate | WorkflowStatus | IsOverdue | DisplayStatus
MDR-0001 | PRJ-024 | Rotating Equipment Spec | Mechanical | B. Okafor | 1 | 2026-02-11 | 2026-03-01 | Approved / IFI | FALSE | Complete
MDR-0002 | PRJ-024 | Vessel Mechanical Design | Mechanical | Q. Chukwu | 2 | 2026-02-27 | 2026-04-04 | Approved / IFI | FALSE | Complete
MDR-0003 | PRJ-024 | Tie-in Schedule | Piping | I. Ogundele | 3 | 2026-04-09 | 2026-04-28 | Approved / IFI | FALSE | Complete
MDR-0004 | PRJ-024 | Cause & Effect Diagram - OML 4 | Instrumentation | S. Uzoma | 1 | 2026-03-04 | 2026-03-27 | Approved / IFI | FALSE | Complete
MDR-0005 | PRJ-024 | Line List | Piping | U. Chukwuemeka | 3 | 2026-02-18 | 2026-03-05 | Approved / IFI | FALSE | Complete
MDR-0006 | PRJ-024 | Compressor Datasheet - OML 4 | Mechanical | B. Okafor | 3 | 2026-05-24 | 2026-06-16 | Approved / IFI | FALSE | Complete
MDR-0007 | PRJ-024 | Corrosion Assessment Report - OML 4 | Pipeline | C. Ibrahim | 4 | 2026-02-15 | 2026-03-02 | Approved / IFI | FALSE | Complete
MDR-0008 | PRJ-024 | Electrical Design Basis | Electrical | M. Ekong | 4 | 2026-05-05 | 2026-06-13 | Approved / IFI | FALSE | Complete
MDR-0009 | PRJ-024 | Pipe Support Register - OML 4 | Piping | U. Chukwuemeka | 4 | 2026-05-27 | 2026-06-27 | Approved / IFI | FALSE | Complete
MDR-0010 | PRJ-024 | Instrument Index | Instrumentation | S. Aliyu | 1 | 2026-06-24 | 2026-07-23 | Approved / IFI | FALSE | Complete
MDR-0011 | PRJ-024 | SCADA Architecture Drawing - OML 4 | Instrumentation | I. Briggs | 1 | 2026-06-15 | 2026-07-09 | Approved / IFI | FALSE | Complete
MDR-0012 | PRJ-024 | Mechanical Handling Study | Mechanical | B. Okafor | 0 | 2026-04-12 | 2026-05-17 | Approved / IFI | FALSE | Complete
MDR-0013 | PRJ-024 | Loop Diagram | Instrumentation | I. Briggs | 4 | 2026-05-24 | 2026-06-09 | Approved / IFI | FALSE | Complete
MDR-0014 | PRJ-024 | Material Take-Off | Piping | U. Chukwuemeka | 3 | 2026-05-22 | 2026-06-14 | Approved / IFI | FALSE | Complete
MDR-0015 | PRJ-024 | Cause & Effect Diagram - OML 4 | Instrumentation | S. Uzoma | 3 | 2026-01-13 | 2026-02-06 | Approved / IFI | FALSE | Complete
MDR-0016 | PRJ-024 | Process Design Basis - OML 4 | Process | A. Musa | 0 | 2026-07-06 | 2026-08-08 | Approved / IFI | FALSE | Complete
MDR-0017 | PRJ-024 | Corrosion Assessment Report | Pipeline | C. Ibrahim | 4 | 2026-02-25 | 2026-03-25 | Approved / IFI | FALSE | Complete
MDR-0018 | PRJ-024 | P&ID | Process | A. Musa | 4 | 2026-07-04 | 2026-07-22 | Approved / IFI | FALSE | Complete
MDR-0019 | PRJ-024 | Pipe Support Register | Piping | E. Okoro | 0 | 2026-07-02 | 2026-07-28 | Issued for Review | TRUE | Overdue
MDR-0020 | PRJ-024 | Loop Diagram - OML 4 | Instrumentation | S. Uzoma | 4 | 2026-09-18 | 2026-10-22 | Revise & Resubmit | FALSE | Revise
MDR-0021 | PRJ-024 | Control Narrative | Instrumentation | H. Sanni | 2 | 2026-07-22 | 2026-08-26 | Revise & Resubmit | FALSE | Revise
MDR-0022 | PRJ-024 | Piping GA Drawing - OML 4 | Piping | I. Ogundele | 0 | 2026-08-31 | 2026-09-17 | Internal Development | FALSE | In Progress
MDR-0023 | PRJ-021 | Loop Diagram | Instrumentation | I. Briggs | 3 | 2026-02-20 | 2026-03-26 | Approved / IFI | FALSE | Complete
MDR-0024 | PRJ-021 | Load List | Electrical | C. James | 4 | 2026-05-31 | 2026-06-20 | Approved / IFI | FALSE | Complete
MDR-0025 | PRJ-021 | Tie-in Schedule | Piping | U. Chukwuemeka | 3 | 2026-03-10 | 2026-04-08 | Approved / IFI | FALSE | Complete
MDR-0026 | PRJ-021 | Instrument Index - OML 7 | Instrumentation | S. Aliyu | 3 | 2026-02-16 | 2026-03-20 | Approved / IFI | FALSE | Complete
MDR-0027 | PRJ-021 | Piping Isometric | Piping | U. Chukwuemeka | 3 | 2026-06-15 | 2026-07-11 | Approved / IFI | FALSE | Complete
MDR-0028 | PRJ-021 | Process Flow Diagram | Process | S. Aliyu | 4 | 2026-03-18 | 2026-03-29 | Approved / IFI | FALSE | Complete
MDR-0029 | PRJ-021 | Process Datasheet - OML 7 | Process | G. Chukwu | 1 | 2026-01-17 | 2026-02-23 | Approved / IFI | FALSE | Complete
MDR-0030 | PRJ-021 | Relief & Blowdown Study | Process | N. Effiong | 4 | 2026-06-09 | 2026-07-02 | Approved / IFI | FALSE | Complete
MDR-0031 | PRJ-021 | Process Design Basis | Process | G. Chukwu | 3 | 2026-05-21 | 2026-06-24 | Approved / IFI | FALSE | Complete
MDR-0032 | PRJ-021 | SCADA Architecture Drawing - OML 7 | Instrumentation | H. Sanni | 2 | 2026-04-12 | 2026-05-16 | Approved / IFI | FALSE | Complete
MDR-0033 | PRJ-021 | Line List | Piping | U. Chukwuemeka | 1 | 2026-01-28 | 2026-02-15 | Approved / IFI | FALSE | Complete
MDR-0034 | PRJ-021 | Single Line Diagram | Electrical | C. James | 0 | 2026-03-07 | 2026-04-12 | Approved / IFI | FALSE | Complete
MDR-0035 | PRJ-021 | Process Flow Diagram | Process | A. Musa | 3 | 2026-06-27 | 2026-07-25 | Approved / IFI | FALSE | Complete
MDR-0036 | PRJ-021 | Rotating Equipment Spec | Mechanical | A. Ihejirika | 3 | 2026-01-12 | 2026-02-04 | Approved / IFI | FALSE | Complete
MDR-0037 | PRJ-021 | Control Narrative - OML 7 | Instrumentation | S. Aliyu | 1 | 2026-08-17 | 2026-09-02 | Internal Development | FALSE | In Progress
MDR-0038 | PRJ-021 | Pump Datasheet - OML 7 | Mechanical | A. Ihejirika | 1 | 2026-09-14 | 2026-10-08 | Revise & Resubmit | FALSE | Revise
MDR-0039 | PRJ-021 | Pipeline Design Basis | Pipeline | C. Ibrahim | 4 | 2026-09-27 | 2026-10-28 | Internal Development | FALSE | In Progress
MDR-0040 | PRJ-021 | Instrument Datasheet - OML 7 | Instrumentation | I. Briggs | 2 | 2026-09-30 | 2026-10-18 | Revise & Resubmit | FALSE | Revise
MDR-0041 | PRJ-021 | Pipe Support Register - OML 7 | Piping | U. Chukwuemeka | 0 | 2026-09-20 | 2026-10-16 | Issued for Review | FALSE | In Review
MDR-0042 | PRJ-021 | Cable Schedule | Electrical | C. James | 3 | 2026-07-07 | 2026-08-05 | Internal Development | TRUE | Overdue
MDR-0043 | PRJ-021 | Cause & Effect Diagram - OML 7 | Instrumentation | I. Briggs | 4 | 2026-08-07 | 2026-08-23 | Revise & Resubmit | FALSE | Revise
MDR-0044 | PRJ-021 | Pump Datasheet | Mechanical | A. Ihejirika | 2 | 2026-09-28 | 2026-10-14 | Issued for Review | FALSE | In Review
MDR-0045 | PRJ-018 | Instrument Datasheet | Instrumentation | I. Briggs | 3 | 2026-02-21 | 2026-03-19 | Approved / IFI | FALSE | Complete
MDR-0046 | PRJ-018 | Foundation Design Report | Civil / Structural | T. Ogundele | 2 | 2026-04-02 | 2026-04-18 | Approved / IFI | FALSE | Complete
MDR-0047 | PRJ-018 | Pigging Study - OML 2 | Pipeline | R. Balogun | 4 | 2026-07-26 | 2026-08-09 | Approved / IFI | FALSE | Complete
MDR-0048 | PRJ-018 | Motor Datasheet - OML 2 | Electrical | R. Ogunleye | 0 | 2026-05-06 | 2026-06-03 | Approved / IFI | FALSE | Complete
MDR-0049 | PRJ-018 | Instrument Datasheet - OML 2 | Instrumentation | S. Uzoma | 1 | 2026-06-03 | 2026-06-15 | Approved / IFI | FALSE | Complete
MDR-0050 | PRJ-018 | Compressor Datasheet | Mechanical | B. Yusuf | 0 | 2026-01-23 | 2026-02-22 | Approved / IFI | FALSE | Complete
MDR-0051 | PRJ-018 | Process Flow Diagram | Process | N. Effiong | 0 | 2026-06-23 | 2026-07-19 | Approved / IFI | FALSE | Complete
MDR-0052 | PRJ-018 | Pipeline Design Basis - OML 2 | Pipeline | R. Balogun | 0 | 2026-07-15 | 2026-07-27 | Approved / IFI | FALSE | Complete
MDR-0053 | PRJ-018 | Structural GA Drawing - OML 2 | Civil / Structural | M. Yakubu | 0 | 2025-12-23 | 2026-01-28 | Approved / IFI | FALSE | Complete
MDR-0054 | PRJ-018 | Loop Diagram - OML 2 | Instrumentation | H. Sanni | 0 | 2026-08-15 | 2026-09-28 | Issued for Review | FALSE | In Review
MDR-0055 | PRJ-018 | Piping Stress Report | Mechanical | B. Yusuf | 3 | 2026-07-10 | 2026-07-27 | Comments Received | TRUE | Overdue
MDR-0056 | PRJ-018 | Pigging Study | Pipeline | R. Balogun | 1 | 2026-09-24 | 2026-10-19 | Revise & Resubmit | FALSE | Revise
MDR-0057 | PRJ-018 | Pump Datasheet | Mechanical | B. Okafor | 1 | 2026-08-27 | 2026-09-27 | Issued for Review | FALSE | In Review
MDR-0058 | PRJ-018 | Compressor Datasheet | Mechanical | B. Okafor | 1 | 2026-08-10 | 2026-09-01 | Internal Development | FALSE | In Progress
MDR-0059 | PRJ-018 | Piping Specification | Piping | E. Okoro | 1 | 2026-07-16 | 2026-08-14 | Comments Received | TRUE | Overdue
MDR-0060 | PRJ-018 | Corrosion Assessment Report | Pipeline | C. Ibrahim | 3 | 2026-08-19 | 2026-09-06 | Issued for Review | FALSE | In Review
MDR-0061 | PRJ-018 | Load List | Electrical | R. Ogunleye | 0 | 2026-08-16 | 2026-09-09 | Issued for Review | FALSE | In Review
MDR-0062 | PRJ-018 | SCADA Architecture Drawing | Instrumentation | H. Sanni | 3 | 2026-08-02 | 2026-09-05 | Revise & Resubmit | FALSE | Revise
MDR-0063 | PRJ-018 | Process Simulation Report | Process | G. Chukwu | 3 | 2026-07-23 | 2026-08-24 | Issued for Review | FALSE | In Review
MDR-0064 | PRJ-015 | Loop Diagram | Instrumentation | S. Aliyu | 2 | 2026-03-14 | 2026-04-01 | Approved / IFI | FALSE | Complete
MDR-0065 | PRJ-015 | Relief & Blowdown Study - OML 10 | Process | G. Chukwu | 1 | 2026-07-11 | 2026-07-23 | Approved / IFI | FALSE | Complete
MDR-0066 | PRJ-015 | Piping Isometric | Piping | I. Ogundele | 1 | 2026-07-07 | 2026-07-20 | Approved / IFI | FALSE | Complete
MDR-0067 | PRJ-015 | Instrument Index | Instrumentation | S. Aliyu | 3 | 2026-01-18 | 2026-02-09 | Approved / IFI | FALSE | Complete
MDR-0068 | PRJ-015 | Cause & Effect Diagram | Instrumentation | S. Aliyu | 0 | 2026-05-20 | 2026-05-31 | Approved / IFI | FALSE | Complete
MDR-0069 | PRJ-015 | Equipment Datasheet | Mechanical | A. Ihejirika | 3 | 2026-01-19 | 2026-02-16 | Approved / IFI | FALSE | Complete
MDR-0070 | PRJ-015 | Instrument Datasheet | Instrumentation | I. Briggs | 2 | 2026-03-23 | 2026-04-03 | Approved / IFI | FALSE | Complete
MDR-0071 | PRJ-015 | Process Flow Diagram - OML 10 | Process | J. Musa | 0 | 2026-02-21 | 2026-03-09 | Approved / IFI | FALSE | Complete
MDR-0072 | PRJ-015 | Piping Isometric | Piping | E. Okoro | 0 | 2026-02-24 | 2026-03-26 | Approved / IFI | FALSE | Complete
MDR-0073 | PRJ-015 | Material Take-Off | Piping | E. Okoro | 0 | 2026-03-10 | 2026-03-28 | Approved / IFI | FALSE | Complete
MDR-0074 | PRJ-015 | Pipe Support Register | Piping | E. Danjuma | 1 | 2026-05-02 | 2026-05-25 | Approved / IFI | FALSE | Complete
MDR-0075 | PRJ-015 | Vessel Mechanical Design | Mechanical | B. Yusuf | 3 | 2026-06-26 | 2026-07-30 | Comments Received | TRUE | Overdue
MDR-0076 | PRJ-015 | P&ID | Process | A. Musa | 3 | 2026-08-24 | 2026-10-02 | Internal Development | FALSE | In Progress
MDR-0077 | PRJ-015 | Motor Datasheet | Electrical | R. Ogunleye | 3 | 2026-07-07 | 2026-08-13 | Internal Development | TRUE | Overdue
MDR-0078 | PRJ-015 | Process Simulation Report | Process | J. Ibrahim | 0 | 2026-07-27 | 2026-08-27 | Internal Development | FALSE | In Progress
MDR-0079 | PRJ-015 | Line List | Piping | E. Danjuma | 3 | 2026-08-13 | 2026-09-07 | Issued for Review | FALSE | In Review
MDR-0080 | PRJ-015 | Process Design Basis | Process | A. Musa | 4 | 2026-07-11 | 2026-08-07 | Comments Received | TRUE | Overdue
MDR-0081 | PRJ-015 | P&ID | Process | G. Chukwu | 3 | 2026-09-10 | 2026-09-25 | Issued for Review | FALSE | In Review
MDR-0082 | PRJ-011 | SCADA Architecture Drawing | Instrumentation | I. Briggs | 4 | 2026-05-11 | 2026-05-21 | Approved / IFI | FALSE | Complete
MDR-0083 | PRJ-011 | HAZOP Report - OML 1 | Process | G. Chukwu | 2 | 2026-05-27 | 2026-06-27 | Approved / IFI | FALSE | Complete
MDR-0084 | PRJ-011 | Earthing Layout | Electrical | F. Etim | 3 | 2026-07-16 | 2026-07-28 | Approved / IFI | FALSE | Complete
MDR-0085 | PRJ-011 | Motor Datasheet - OML 1 | Electrical | F. Etim | 2 | 2026-05-13 | 2026-06-06 | Approved / IFI | FALSE | Complete
MDR-0086 | PRJ-011 | Instrument Index - OML 1 | Instrumentation | H. Sanni | 4 | 2026-06-30 | 2026-07-19 | Approved / IFI | FALSE | Complete
MDR-0087 | PRJ-011 | Cable Schedule | Electrical | R. Ogunleye | 0 | 2026-06-03 | 2026-06-25 | Approved / IFI | FALSE | Complete
MDR-0088 | PRJ-011 | Control Narrative - OML 1 | Instrumentation | H. Sanni | 1 | 2026-01-15 | 2026-02-04 | Approved / IFI | FALSE | Complete
MDR-0089 | PRJ-011 | Piping Stress Report | Mechanical | A. Ihejirika | 1 | 2026-05-15 | 2026-06-18 | Approved / IFI | FALSE | Complete
MDR-0090 | PRJ-011 | Material Take-Off | Piping | E. Okoro | 2 | 2026-02-04 | 2026-03-09 | Approved / IFI | FALSE | Complete
MDR-0091 | PRJ-011 | Instrument Index - OML 1 | Instrumentation | S. Aliyu | 4 | 2026-04-05 | 2026-04-20 | Approved / IFI | FALSE | Complete
MDR-0092 | PRJ-011 | Lifting Plan | Mechanical | B. Okafor | 0 | 2026-02-24 | 2026-03-12 | Approved / IFI | FALSE | Complete
MDR-0093 | PRJ-011 | Tie-in Schedule | Piping | E. Okoro | 1 | 2026-02-22 | 2026-03-15 | Approved / IFI | FALSE | Complete
MDR-0094 | PRJ-011 | Cause & Effect Diagram | Instrumentation | I. Briggs | 4 | 2026-04-30 | 2026-05-24 | Approved / IFI | FALSE | Complete
MDR-0095 | PRJ-011 | Process Flow Diagram | Process | G. Chukwu | 3 | 2026-01-16 | 2026-02-11 | Approved / IFI | FALSE | Complete
MDR-0096 | PRJ-011 | Material Take-Off | Piping | E. Okoro | 2 | 2026-02-02 | 2026-02-26 | Approved / IFI | FALSE | Complete
MDR-0097 | PRJ-011 | Piping Isometric | Piping | I. Ogundele | 3 | 2026-07-07 | 2026-07-29 | Approved / IFI | FALSE | Complete
MDR-0098 | PRJ-011 | Process Simulation Report | Process | J. Musa | 4 | 2026-10-03 | 2026-10-18 | Comments Received | FALSE | In Review
MDR-0099 | GLB-003 | Piping GA Drawing | Piping | I. Ogundele | 4 | 2026-01-31 | 2026-02-28 | Approved / IFI | FALSE | Complete
MDR-0100 | GLB-003 | Earthing Layout | Electrical | F. Etim | 2 | 2026-04-17 | 2026-05-18 | Approved / IFI | FALSE | Complete
MDR-0101 | GLB-003 | Process Flow Diagram - Global | Process | N. Effiong | 2 | 2026-06-12 | 2026-07-04 | Approved / IFI | FALSE | Complete
MDR-0102 | GLB-003 | Piping GA Drawing | Piping | U. Chukwuemeka | 2 | 2026-03-13 | 2026-03-27 | Approved / IFI | FALSE | Complete
MDR-0103 | GLB-003 | Process Design Basis | Process | J. Musa | 2 | 2026-01-16 | 2026-02-18 | Approved / IFI | FALSE | Complete
MDR-0104 | GLB-003 | Process Simulation Report | Process | J. Musa | 3 | 2026-06-22 | 2026-07-20 | Approved / IFI | FALSE | Complete
MDR-0105 | GLB-003 | Material Take-Off | Piping | E. Danjuma | 1 | 2026-01-17 | 2026-02-22 | Approved / IFI | FALSE | Complete
MDR-0106 | GLB-003 | Piping Isometric | Piping | E. Danjuma | 4 | 2026-10-04 | 2026-10-25 | Internal Development | FALSE | In Progress
MDR-0107 | GLB-003 | Steelwork Fabrication Drawing - Global | Civil / Structural | N. Uzoma | 3 | 2026-06-24 | 2026-08-05 | Revise & Resubmit | TRUE | Overdue
MDR-0108 | GLB-003 | Single Line Diagram | Electrical | R. Ogunleye | 4 | 2026-08-23 | 2026-09-17 | Internal Development | FALSE | In Progress
MDR-0109 | GLB-003 | Pipe Support Register | Piping | U. Chukwuemeka | 3 | 2026-07-28 | 2026-08-18 | Comments Received | FALSE | In Review
MDR-0110 | GLB-003 | Electrical Design Basis - Global | Electrical | C. James | 3 | 2026-07-01 | 2026-08-02 | Internal Development | TRUE | Overdue
MDR-0111 | GLB-003 | Motor Datasheet | Electrical | M. Ekong | 2 | 2026-08-24 | 2026-09-24 | Internal Development | FALSE | In Progress
MDR-0112 | GLB-003 | Equipment Datasheet | Mechanical | B. Yusuf | 4 | 2026-08-16 | 2026-09-18 | Comments Received | FALSE | In Review
MDR-0113 | GLB-003 | Single Line Diagram - Global | Electrical | R. Ogunleye | 1 | 2026-08-14 | 2026-09-19 | Internal Development | FALSE | In Progress
MDR-0114 | GLB-003 | Pipe Support Register | Piping | P. Ndukwe | 1 | 2026-08-09 | 2026-08-25 | Revise & Resubmit | FALSE | Revise
MDR-0115 | GLB-003 | HAZOP Report - Global | Process | G. Chukwu | 1 | 2026-07-20 | 2026-08-26 | Issued for Review | FALSE | In Review
MDR-0116 | GLB-003 | Instrument Datasheet | Instrumentation | I. Briggs | 4 | 2026-09-14 | 2026-10-02 | Issued for Review | FALSE | In Review
MDR-0117 | GLB-003 | Instrument Datasheet | Instrumentation | H. Sanni | 0 | 2026-09-12 | 2026-10-13 | Issued for Review | FALSE | In Review
MDR-0118 | GLB-003 | Steelwork Fabrication Drawing | Civil / Structural | N. Uzoma | 0 | 2026-08-17 | 2026-09-08 | Issued for Review | FALSE | In Review
MDR-0119 | PRJ-006 | Relief & Blowdown Study | Process | S. Aliyu | 4 | 2026-03-03 | 2026-04-04 | Approved / IFI | FALSE | Complete
MDR-0120 | PRJ-006 | P&ID - OML 1 | Process | N. Effiong | 4 | 2026-05-09 | 2026-06-05 | Approved / IFI | FALSE | Complete
MDR-0121 | PRJ-006 | Steelwork Fabrication Drawing - OML 1 | Civil / Structural | T. Ogundele | 4 | 2026-01-21 | 2026-02-05 | Approved / IFI | FALSE | Complete
MDR-0122 | PRJ-006 | Electrical Design Basis - OML 1 | Electrical | F. Etim | 2 | 2026-01-17 | 2026-02-03 | Approved / IFI | FALSE | Complete
MDR-0123 | PRJ-006 | Process Flow Diagram - OML 1 | Process | J. Ibrahim | 1 | 2026-03-21 | 2026-04-26 | Approved / IFI | FALSE | Complete
MDR-0124 | PRJ-006 | Structural GA Drawing | Civil / Structural | T. Ogundele | 2 | 2026-04-24 | 2026-05-29 | Approved / IFI | FALSE | Complete
MDR-0125 | PRJ-006 | Cable Schedule | Electrical | M. Ekong | 0 | 2026-01-15 | 2026-02-21 | Approved / IFI | FALSE | Complete
MDR-0126 | PRJ-006 | Cause & Effect Diagram - OML 1 | Instrumentation | I. Briggs | 2 | 2026-04-24 | 2026-05-16 | Approved / IFI | FALSE | Complete
MDR-0127 | PRJ-006 | Tie-in Schedule | Piping | E. Danjuma | 2 | 2026-01-28 | 2026-02-15 | Approved / IFI | FALSE | Complete
MDR-0128 | PRJ-006 | Heat & Material Balance - OML 1 | Process | S. Aliyu | 1 | 2026-03-30 | 2026-05-03 | Approved / IFI | FALSE | Complete
MDR-0129 | PRJ-006 | Pipe Support Register | Piping | U. Chukwuemeka | 3 | 2026-04-25 | 2026-05-15 | Approved / IFI | FALSE | Complete
MDR-0130 | PRJ-006 | Process Simulation Report | Process | A. Musa | 4 | 2026-02-11 | 2026-03-06 | Approved / IFI | FALSE | Complete
MDR-0131 | PRJ-006 | Pipe Support Register | Piping | P. Ndukwe | 0 | 2026-06-03 | 2026-06-14 | Approved / IFI | FALSE | Complete
MDR-0132 | PRJ-006 | Relief & Blowdown Study | Process | S. Aliyu | 0 | 2026-06-29 | 2026-08-02 | Approved / IFI | FALSE | Complete
MDR-0133 | PRJ-006 | Mechanical Handling Study - OML 1 | Mechanical | B. Yusuf | 4 | 2026-06-24 | 2026-07-06 | Approved / IFI | FALSE | Complete
MDR-0134 | PRJ-006 | Pipe Support Register - OML 1 | Piping | U. Chukwuemeka | 3 | 2026-08-09 | 2026-09-17 | Internal Development | FALSE | In Progress
MDR-0135 | PRJ-009 | Compressor Datasheet | Mechanical | B. Okafor | 4 | 2026-05-12 | 2026-06-12 | Approved / IFI | FALSE | Complete
MDR-0136 | PRJ-009 | Structural GA Drawing | Civil / Structural | N. Uzoma | 3 | 2026-07-02 | 2026-07-23 | Approved / IFI | FALSE | Complete
MDR-0137 | PRJ-009 | Process Flow Diagram | Process | S. Aliyu | 2 | 2026-02-05 | 2026-03-01 | Approved / IFI | FALSE | Complete
MDR-0138 | PRJ-009 | Relief & Blowdown Study | Process | N. Effiong | 3 | 2026-01-13 | 2026-02-05 | Approved / IFI | FALSE | Complete
MDR-0139 | PRJ-009 | Tie-in Schedule | Piping | U. Chukwuemeka | 4 | 2026-04-19 | 2026-05-21 | Approved / IFI | FALSE | Complete
MDR-0140 | PRJ-009 | Load List | Electrical | F. Etim | 1 | 2026-01-23 | 2026-02-15 | Approved / IFI | FALSE | Complete
MDR-0141 | PRJ-009 | Electrical Design Basis | Electrical | C. James | 1 | 2026-02-16 | 2026-03-02 | Approved / IFI | FALSE | Complete
MDR-0142 | PRJ-009 | Electrical Design Basis | Electrical | R. Ogunleye | 0 | 2026-05-06 | 2026-05-26 | Approved / IFI | FALSE | Complete
MDR-0143 | PRJ-009 | Piping GA Drawing - OML 4 | Piping | I. Ogundele | 2 | 2026-01-31 | 2026-02-17 | Approved / IFI | FALSE | Complete
MDR-0144 | PRJ-009 | Process Simulation Report | Process | A. Musa | 4 | 2025-12-29 | 2026-01-29 | Approved / IFI | FALSE | Complete
MDR-0145 | PRJ-009 | Process Simulation Report | Process | N. Effiong | 3 | 2026-07-10 | 2026-08-05 | Approved / IFI | FALSE | Complete
MDR-0146 | PRJ-009 | Pipe Support Register - OML 4 | Piping | E. Danjuma | 4 | 2026-07-05 | 2026-07-18 | Approved / IFI | FALSE | Complete
MDR-0147 | PRJ-009 | Load List | Electrical | C. James | 2 | 2026-05-21 | 2026-06-28 | Approved / IFI | FALSE | Complete
MDR-0148 | PRJ-009 | Earthing Layout | Electrical | M. Ekong | 4 | 2026-01-28 | 2026-02-10 | Approved / IFI | FALSE | Complete
MDR-0149 | PRJ-009 | Single Line Diagram | Electrical | M. Ekong | 4 | 2026-05-05 | 2026-06-10 | Approved / IFI | FALSE | Complete
MDR-0150 | PRJ-009 | Process Design Basis | Process | J. Ibrahim | 2 | 2026-05-24 | 2026-06-20 | Approved / IFI | FALSE | Complete
MDR-0151 | PRJ-009 | Heat & Material Balance | Process | J. Ibrahim | 3 | 2026-01-09 | 2026-02-01 | Approved / IFI | FALSE | Complete
MDR-0152 | PRJ-009 | SCADA Architecture Drawing | Instrumentation | H. Sanni | 3 | 2026-01-15 | 2026-02-11 | Approved / IFI | FALSE | Complete
MDR-0153 | PRJ-009 | Piping Specification | Piping | U. Chukwuemeka | 2 | 2026-10-01 | 2026-10-16 | Internal Development | FALSE | In Progress
MDR-0154 | PRJ-005 | Instrument Datasheet | Instrumentation | S. Aliyu | 2 | 2026-01-19 | 2026-02-09 | Approved / IFI | FALSE | Complete
MDR-0155 | PRJ-005 | Material Take-Off | Piping | E. Danjuma | 2 | 2026-02-14 | 2026-03-18 | Approved / IFI | FALSE | Complete
MDR-0156 | PRJ-005 | Process Datasheet | Process | J. Musa | 0 | 2026-02-04 | 2026-03-03 | Approved / IFI | FALSE | Complete
MDR-0157 | PRJ-005 | Earthing Layout | Electrical | R. Ogunleye | 0 | 2026-06-21 | 2026-07-22 | Internal Development | TRUE | Overdue
MDR-0158 | PRJ-005 | Compressor Datasheet | Mechanical | A. Ihejirika | 3 | 2026-07-15 | 2026-08-23 | Issued for Review | FALSE | In Review
MDR-0159 | PRJ-005 | Piping Specification | Piping | E. Okoro | 2 | 2026-07-06 | 2026-07-25 | Comments Received | TRUE | Overdue
MDR-0160 | PRJ-005 | Single Line Diagram | Electrical | F. Etim | 4 | 2026-07-14 | 2026-08-08 | Issued for Review | TRUE | Overdue
MDR-0161 | PRJ-005 | Piping Stress Report | Mechanical | B. Okafor | 0 | 2026-09-08 | 2026-10-18 | Internal Development | FALSE | In Progress
MDR-0162 | PRJ-005 | Cable Schedule | Electrical | F. Etim | 2 | 2026-08-31 | 2026-09-27 | Issued for Review | FALSE | In Review
MDR-0163 | PRJ-005 | Piping Specification | Piping | E. Danjuma | 3 | 2026-06-17 | 2026-07-31 | Issued for Review | TRUE | Overdue
MDR-0164 | PRJ-005 | Material Take-Off | Piping | P. Ndukwe | 2 | 2026-07-30 | 2026-08-17 | Comments Received | FALSE | In Review
MDR-0165 | PRJ-008 | HAZOP Report | Process | J. Ibrahim | 4 | 2026-02-09 | 2026-03-04 | Approved / IFI | FALSE | Complete
MDR-0166 | PRJ-008 | Geotechnical Report | Civil / Structural | M. Yakubu | 2 | 2026-02-26 | 2026-03-16 | Approved / IFI | FALSE | Complete
MDR-0167 | PRJ-008 | Piping Specification - OML 4 | Piping | E. Danjuma | 4 | 2026-07-15 | 2026-08-01 | Internal Development | TRUE | Overdue
MDR-0168 | PRJ-008 | Compressor Datasheet | Mechanical | B. Okafor | 4 | 2026-08-04 | 2026-09-13 | Internal Development | FALSE | In Progress
MDR-0169 | PRJ-008 | Pipeline Route Survey | Pipeline | C. Ibrahim | 1 | 2026-08-02 | 2026-08-26 | Issued for Review | FALSE | In Review
MDR-0170 | PRJ-008 | Pump Datasheet | Mechanical | B. Yusuf | 0 | 2026-07-03 | 2026-08-12 | Comments Received | TRUE | Overdue
MDR-0171 | PRJ-008 | Equipment Datasheet - OML 4 | Mechanical | A. Ihejirika | 3 | 2026-09-15 | 2026-10-05 | Internal Development | FALSE | In Progress
MDR-0172 | PRJ-008 | Pump Datasheet | Mechanical | Q. Chukwu | 0 | 2026-09-15 | 2026-10-26 | Issued for Review | FALSE | In Review
MDR-0173 | PRJ-008 | Heat & Material Balance - OML 4 | Process | J. Musa | 0 | 2026-08-24 | 2026-09-25 | Issued for Review | FALSE | In Review
MDR-0174 | PRJ-008 | Piping Specification | Piping | E. Okoro | 2 | 2026-09-19 | 2026-10-07 | Comments Received | FALSE | In Review
MDR-0175 | PRJ-008 | Line List | Piping | E. Okoro | 3 | 2026-09-29 | 2026-10-19 | Comments Received | FALSE | In Review
MDR-0176 | PRJ-008 | Instrument Datasheet - OML 4 | Instrumentation | I. Briggs | 2 | 2026-08-16 | 2026-09-07 | Internal Development | FALSE | In Progress
MDR-0177 | PRJ-008 | Cable Schedule | Electrical | M. Ekong | 3 | 2026-07-27 | 2026-08-12 | Comments Received | TRUE | Overdue
MDR-0178 | PRJ-013 | Piping Stress Report | Mechanical | B. Yusuf | 1 | 2026-04-14 | 2026-05-16 | Approved / IFI | FALSE | Complete
MDR-0179 | PRJ-013 | Process Simulation Report | Process | N. Effiong | 4 | 2026-01-30 | 2026-02-27 | Approved / IFI | FALSE | Complete
MDR-0180 | PRJ-013 | Process Flow Diagram | Process | N. Effiong | 2 | 2026-04-25 | 2026-05-30 | Approved / IFI | FALSE | Complete
MDR-0181 | PRJ-013 | Vessel Mechanical Design | Mechanical | D. Umeh | 4 | 2026-04-02 | 2026-04-22 | Approved / IFI | FALSE | Complete
MDR-0182 | PRJ-013 | Control Narrative - OML 5 | Instrumentation | S. Aliyu | 2 | 2026-10-04 | 2026-10-24 | Comments Received | FALSE | In Review
MDR-0183 | PRJ-013 | Vessel Mechanical Design | Mechanical | B. Okafor | 0 | 2026-08-29 | 2026-10-03 | Issued for Review | FALSE | In Review
MDR-0184 | PRJ-013 | Piping GA Drawing | Piping | E. Danjuma | 4 | 2026-09-22 | 2026-10-09 | Revise & Resubmit | FALSE | Revise
MDR-0185 | PRJ-013 | Lifting Plan | Mechanical | B. Okafor | 4 | 2026-07-09 | 2026-08-03 | Comments Received | TRUE | Overdue
MDR-0186 | PRJ-013 | Control Narrative | Instrumentation | H. Sanni | 2 | 2026-08-27 | 2026-10-09 | Internal Development | FALSE | In Progress
MDR-0187 | PRJ-013 | Single Line Diagram - OML 5 | Electrical | M. Ekong | 2 | 2026-09-21 | 2026-10-10 | Comments Received | FALSE | In Review
MDR-0188 | PRJ-013 | Pigging Study | Pipeline | R. Balogun | 3 | 2026-08-14 | 2026-09-17 | Internal Development | FALSE | In Progress
MDR-0189 | PRJ-013 | Relief & Blowdown Study | Process | S. Aliyu | 2 | 2026-07-19 | 2026-09-01 | Internal Development | FALSE | In Progress
MDR-0190 | PRJ-013 | Earthing Layout | Electrical | C. James | 0 | 2026-08-09 | 2026-08-26 | Issued for Review | FALSE | In Review
MDR-0191 | PRJ-013 | Motor Datasheet - OML 5 | Electrical | R. Ogunleye | 2 | 2026-07-10 | 2026-08-14 | Issued for Review | TRUE | Overdue
MDR-0192 | PRJ-013 | Pipeline Crossing Design - OML 5 | Pipeline | C. Ibrahim | 1 | 2026-07-12 | 2026-08-24 | Internal Development | FALSE | In Progress
MDR-0193 | PRJ-013 | Instrument Datasheet - OML 5 | Instrumentation | H. Sanni | 4 | 2026-08-01 | 2026-09-11 | Revise & Resubmit | FALSE | Revise
MDR-0194 | PRJ-019 | Motor Datasheet | Electrical | C. James | 2 | 2026-05-05 | 2026-06-09 | Approved / IFI | FALSE | Complete
MDR-0195 | PRJ-019 | Piping Specification - OML 7 | Piping | U. Chukwuemeka | 4 | 2026-10-10 | 2026-10-28 | Internal Development | FALSE | In Progress
MDR-0196 | PRJ-019 | Pipeline Crossing Design - OML 7 | Pipeline | C. Ibrahim | 1 | 2026-09-20 | 2026-10-24 | Revise & Resubmit | FALSE | Revise
MDR-0197 | PRJ-019 | SCADA Architecture Drawing | Instrumentation | H. Sanni | 1 | 2026-09-10 | 2026-10-21 | Revise & Resubmit | FALSE | Revise
MDR-0198 | PRJ-019 | Single Line Diagram | Electrical | C. James | 3 | 2026-08-30 | 2026-09-23 | Revise & Resubmit | FALSE | Revise
MDR-0199 | PRJ-019 | Electrical Design Basis | Electrical | F. Etim | 0 | 2026-07-28 | 2026-09-04 | Revise & Resubmit | FALSE | Revise
MDR-0200 | PRJ-019 | Rotating Equipment Spec - OML 7 | Mechanical | B. Yusuf | 4 | 2026-09-23 | 2026-10-25 | Comments Received | FALSE | In Review
MDR-0201 | PRJ-019 | Geotechnical Report - OML 7 | Civil / Structural | M. Yakubu | 0 | 2026-06-17 | 2026-07-29 | Revise & Resubmit | TRUE | Overdue
MDR-0202 | PRJ-023 | Pigging Study - OML 10 | Pipeline | C. Ibrahim | 3 | 2026-01-19 | 2026-02-23 | Approved / IFI | FALSE | Complete
MDR-0203 | PRJ-023 | Mechanical Handling Study - OML 10 | Mechanical | B. Yusuf | 2 | 2026-06-02 | 2026-06-16 | Approved / IFI | FALSE | Complete
MDR-0204 | PRJ-023 | Piping Stress Report | Mechanical | Q. Chukwu | 4 | 2026-03-20 | 2026-04-13 | Approved / IFI | FALSE | Complete
MDR-0205 | PRJ-023 | Single Line Diagram | Electrical | R. Ogunleye | 0 | 2026-06-16 | 2026-07-28 | Comments Received | TRUE | Overdue
MDR-0206 | PRJ-023 | Heat & Material Balance - OML 10 | Process | G. Chukwu | 4 | 2026-09-27 | 2026-10-28 | Issued for Review | FALSE | In Review
MDR-0207 | PRJ-023 | Relief & Blowdown Study - OML 10 | Process | J. Musa | 3 | 2026-09-07 | 2026-10-02 | Issued for Review | FALSE | In Review
MDR-0208 | PRJ-023 | Process Flow Diagram | Process | J. Musa | 1 | 2026-09-08 | 2026-10-20 | Comments Received | FALSE | In Review
MDR-0209 | PRJ-023 | Material Take-Off | Piping | I. Ogundele | 4 | 2026-06-19 | 2026-07-26 | Internal Development | TRUE | Overdue
MDR-0210 | PRJ-023 | Compressor Datasheet | Mechanical | D. Umeh | 4 | 2026-08-27 | 2026-09-24 | Comments Received | FALSE | In Review
MDR-0211 | PRJ-023 | Material Take-Off | Piping | U. Chukwuemeka | 1 | 2026-09-23 | 2026-10-11 | Issued for Review | FALSE | In Review
MDR-0212 | PRJ-023 | Pipeline Design Basis - OML 10 | Pipeline | R. Balogun | 1 | 2026-09-17 | 2026-10-19 | Issued for Review | FALSE | In Review
MDR-0213 | PRJ-023 | Piping Isometric | Piping | E. Okoro | 2 | 2026-08-11 | 2026-09-09 | Internal Development | FALSE | In Progress
MDR-0214 | PRJ-023 | Lifting Plan | Mechanical | B. Okafor | 3 | 2026-08-24 | 2026-09-26 | Internal Development | FALSE | In Progress
MDR-0215 | GLB-004 | Equipment Datasheet | Mechanical | A. Ihejirika | 1 | 2026-07-05 | 2026-08-06 | Approved / IFI | FALSE | Complete
MDR-0216 | GLB-004 | Compressor Datasheet | Mechanical | Q. Chukwu | 3 | 2026-01-30 | 2026-02-21 | Approved / IFI | FALSE | Complete
MDR-0217 | GLB-004 | Piping Isometric | Piping | E. Okoro | 4 | 2026-06-23 | 2026-07-22 | Approved / IFI | FALSE | Complete
MDR-0218 | GLB-004 | Compressor Datasheet | Mechanical | Q. Chukwu | 3 | 2026-06-14 | 2026-07-03 | Approved / IFI | FALSE | Complete
MDR-0219 | GLB-004 | Cause & Effect Diagram | Instrumentation | S. Aliyu | 1 | 2026-01-11 | 2026-02-13 | Approved / IFI | FALSE | Complete
MDR-0220 | GLB-004 | Single Line Diagram - Global | Electrical | C. James | 3 | 2026-08-27 | 2026-10-02 | Internal Development | FALSE | In Progress
MDR-0221 | GLB-004 | SCADA Architecture Drawing | Instrumentation | H. Sanni | 1 | 2026-06-27 | 2026-08-04 | Issued for Review | TRUE | Overdue
MDR-0222 | GLB-004 | Single Line Diagram - Global | Electrical | F. Etim | 3 | 2026-08-19 | 2026-09-25 | Comments Received | FALSE | In Review
MDR-0223 | GLB-004 | Vessel Mechanical Design | Mechanical | B. Okafor | 1 | 2026-09-02 | 2026-09-27 | Internal Development | FALSE | In Progress
MDR-0224 | GLB-004 | Cause & Effect Diagram - Global | Instrumentation | I. Briggs | 4 | 2026-07-19 | 2026-08-23 | Issued for Review | FALSE | In Review
MDR-0225 | GLB-004 | Tie-in Schedule | Piping | P. Ndukwe | 4 | 2026-07-22 | 2026-08-31 | Issued for Review | FALSE | In Review
MDR-0226 | GLB-004 | Heat & Material Balance | Process | A. Musa | 1 | 2026-09-24 | 2026-10-18 | Issued for Review | FALSE | In Review
MDR-0227 | GLB-004 | Material Take-Off - Global | Piping | P. Ndukwe | 0 | 2026-09-12 | 2026-10-25 | Internal Development | FALSE | In Progress
MDR-0228 | PRJ-001 | Process Simulation Report | Process | N. Effiong | 0 | 2025-12-27 | 2026-01-31 | Approved / IFI | FALSE | Complete
MDR-0229 | PRJ-001 | Pigging Study - OML 1 | Pipeline | R. Balogun | 0 | 2026-05-20 | 2026-06-12 | Approved / IFI | FALSE | Complete
MDR-0230 | PRJ-001 | Pipe Support Register | Piping | U. Chukwuemeka | 1 | 2026-02-08 | 2026-03-08 | Approved / IFI | FALSE | Complete
MDR-0231 | PRJ-001 | Process Simulation Report | Process | J. Ibrahim | 0 | 2026-06-27 | 2026-08-04 | Approved / IFI | FALSE | Complete
MDR-0232 | PRJ-001 | Piping Specification | Piping | I. Ogundele | 4 | 2026-04-11 | 2026-05-18 | Approved / IFI | FALSE | Complete
MDR-0233 | PRJ-001 | Process Datasheet | Process | G. Chukwu | 3 | 2026-06-04 | 2026-07-13 | Approved / IFI | FALSE | Complete
MDR-0234 | PRJ-001 | Line List | Piping | E. Okoro | 1 | 2026-06-11 | 2026-07-13 | Approved / IFI | FALSE | Complete
MDR-0235 | PRJ-001 | Relief & Blowdown Study | Process | A. Musa | 3 | 2026-06-19 | 2026-07-28 | Approved / IFI | FALSE | Complete
MDR-0236 | PRJ-001 | Pigging Study - OML 1 | Pipeline | R. Balogun | 2 | 2026-04-14 | 2026-05-15 | Approved / IFI | FALSE | Complete
MDR-0237 | PRJ-001 | Loop Diagram - OML 1 | Instrumentation | I. Briggs | 1 | 2026-03-24 | 2026-04-14 | Approved / IFI | FALSE | Complete
MDR-0238 | PRJ-001 | Equipment Datasheet - OML 1 | Mechanical | D. Umeh | 3 | 2026-09-14 | 2026-10-09 | Revise & Resubmit | FALSE | Revise
MDR-0239 | PRJ-001 | Load List | Electrical | M. Ekong | 4 | 2026-08-07 | 2026-09-14 | Issued for Review | FALSE | In Review
MDR-0240 | PRJ-001 | Mechanical Handling Study - OML 1 | Mechanical | B. Okafor | 4 | 2026-06-22 | 2026-07-28 | Internal Development | TRUE | Overdue
MDR-0241 | PRJ-001 | Cable Schedule | Electrical | C. James | 2 | 2026-09-25 | 2026-10-11 | Internal Development | FALSE | In Progress
MDR-0242 | PRJ-001 | Line List - OML 1 | Piping | E. Okoro | 1 | 2026-09-22 | 2026-10-14 | Revise & Resubmit | FALSE | Revise
MDR-0243 | PRJ-001 | Vessel Mechanical Design - OML 1 | Mechanical | B. Okafor | 4 | 2026-08-09 | 2026-09-17 | Issued for Review | FALSE | In Review
MDR-0244 | PRJ-001 | Equipment Datasheet | Mechanical | B. Yusuf | 1 | 2026-07-08 | 2026-07-31 | Issued for Review | TRUE | Overdue
MDR-0245 | PRJ-001 | Piping Stress Report | Mechanical | B. Yusuf | 4 | 2026-09-25 | 2026-10-21 | Issued for Review | FALSE | In Review
MDR-0246 | PRJ-001 | Instrument Datasheet - OML 1 | Instrumentation | I. Briggs | 4 | 2026-07-30 | 2026-09-07 | Issued for Review | FALSE | In Review
MDR-0247 | PRJ-001 | Rotating Equipment Spec | Mechanical | D. Umeh | 4 | 2026-08-30 | 2026-10-11 | Issued for Review | FALSE | In Review
MDR-0248 | PRJ-001 | Process Design Basis - OML 1 | Process | N. Effiong | 2 | 2026-09-09 | 2026-10-17 | Issued for Review | FALSE | In Review
MDR-0249 | PRJ-001 | Process Simulation Report | Process | S. Aliyu | 3 | 2026-07-06 | 2026-08-10 | Issued for Review | TRUE | Overdue
MDR-0250 | PRJ-003 | Cable Schedule | Electrical | M. Ekong | 0 | 2026-06-19 | 2026-07-23 | Approved / IFI | FALSE | Complete
MDR-0251 | PRJ-003 | Cable Schedule | Electrical | F. Etim | 2 | 2026-05-10 | 2026-06-07 | Approved / IFI | FALSE | Complete
MDR-0252 | PRJ-003 | Control Narrative - OML 2 | Instrumentation | S. Aliyu | 2 | 2026-02-20 | 2026-03-14 | Approved / IFI | FALSE | Complete
MDR-0253 | PRJ-003 | HAZOP Report | Process | J. Ibrahim | 4 | 2026-01-21 | 2026-02-25 | Approved / IFI | FALSE | Complete
MDR-0254 | PRJ-003 | Instrument Datasheet | Instrumentation | H. Sanni | 0 | 2026-05-07 | 2026-05-27 | Approved / IFI | FALSE | Complete
MDR-0255 | PRJ-003 | Cable Schedule | Electrical | F. Etim | 0 | 2026-01-14 | 2026-02-05 | Approved / IFI | FALSE | Complete
MDR-0256 | PRJ-003 | Piping Specification | Piping | E. Okoro | 1 | 2026-05-24 | 2026-06-19 | Approved / IFI | FALSE | Complete
MDR-0257 | PRJ-003 | Pipeline Design Basis - OML 2 | Pipeline | R. Balogun | 1 | 2026-05-04 | 2026-05-31 | Approved / IFI | FALSE | Complete
MDR-0258 | PRJ-003 | Process Flow Diagram | Process | G. Chukwu | 2 | 2026-07-18 | 2026-08-08 | Approved / IFI | FALSE | Complete
MDR-0259 | PRJ-003 | Piping GA Drawing - OML 2 | Piping | E. Okoro | 1 | 2026-03-20 | 2026-04-02 | Approved / IFI | FALSE | Complete
MDR-0260 | PRJ-003 | Piping GA Drawing | Piping | P. Ndukwe | 1 | 2026-09-04 | 2026-09-19 | Comments Received | FALSE | In Review
MDR-0261 | PRJ-003 | Rotating Equipment Spec - OML 2 | Mechanical | B. Okafor | 4 | 2026-06-23 | 2026-07-25 | Comments Received | TRUE | Overdue
MDR-0262 | PRJ-003 | Pipe Support Register - OML 2 | Piping | U. Chukwuemeka | 1 | 2026-09-29 | 2026-10-17 | Internal Development | FALSE | In Progress
MDR-0263 | PRJ-003 | Instrument Datasheet | Instrumentation | S. Uzoma | 3 | 2026-09-10 | 2026-10-17 | Issued for Review | FALSE | In Review
MDR-0264 | PRJ-003 | Tie-in Schedule | Piping | U. Chukwuemeka | 2 | 2026-09-01 | 2026-09-18 | Internal Development | FALSE | In Progress
MDR-0265 | PRJ-003 | Piping Specification | Piping | P. Ndukwe | 1 | 2026-09-06 | 2026-10-19 | Revise & Resubmit | FALSE | Revise
MDR-0266 | PRJ-007 | Heat & Material Balance | Process | J. Musa | 1 | 2026-01-26 | 2026-02-15 | Approved / IFI | FALSE | Complete
MDR-0267 | PRJ-007 | Pigging Study - OML 4 | Pipeline | C. Ibrahim | 3 | 2026-02-14 | 2026-03-04 | Approved / IFI | FALSE | Complete
MDR-0268 | PRJ-007 | Relief & Blowdown Study | Process | N. Effiong | 1 | 2026-02-27 | 2026-03-09 | Approved / IFI | FALSE | Complete
MDR-0269 | PRJ-007 | Vessel Mechanical Design | Mechanical | B. Okafor | 3 | 2026-04-10 | 2026-04-25 | Approved / IFI | FALSE | Complete
MDR-0270 | PRJ-007 | Corrosion Assessment Report | Pipeline | R. Balogun | 1 | 2026-02-21 | 2026-03-18 | Approved / IFI | FALSE | Complete
MDR-0271 | PRJ-007 | Electrical Design Basis - OML 4 | Electrical | M. Ekong | 4 | 2026-04-23 | 2026-06-01 | Approved / IFI | FALSE | Complete
MDR-0272 | PRJ-007 | Process Simulation Report - OML 4 | Process | N. Effiong | 4 | 2026-02-18 | 2026-03-12 | Approved / IFI | FALSE | Complete
MDR-0273 | PRJ-007 | Process Simulation Report | Process | N. Effiong | 0 | 2026-06-10 | 2026-07-02 | Approved / IFI | FALSE | Complete
MDR-0274 | PRJ-007 | Motor Datasheet | Electrical | R. Ogunleye | 4 | 2026-02-22 | 2026-03-22 | Approved / IFI | FALSE | Complete
MDR-0275 | PRJ-007 | Instrument Datasheet | Instrumentation | I. Briggs | 0 | 2026-05-14 | 2026-06-05 | Approved / IFI | FALSE | Complete
MDR-0276 | PRJ-007 | Steelwork Fabrication Drawing - OML 4 | Civil / Structural | M. Yakubu | 0 | 2026-07-18 | 2026-08-31 | Issued for Review | FALSE | In Review
MDR-0277 | PRJ-007 | Heat & Material Balance - OML 4 | Process | J. Musa | 4 | 2026-07-30 | 2026-09-01 | Comments Received | FALSE | In Review
MDR-0278 | PRJ-007 | Rotating Equipment Spec | Mechanical | B. Yusuf | 0 | 2026-07-17 | 2026-08-04 | Internal Development | TRUE | Overdue
MDR-0279 | PRJ-007 | Load List - OML 4 | Electrical | C. James | 2 | 2026-10-03 | 2026-10-26 | Issued for Review | FALSE | In Review
MDR-0280 | PRJ-007 | Vessel Mechanical Design | Mechanical | Q. Chukwu | 3 | 2026-07-05 | 2026-08-11 | Issued for Review | TRUE | Overdue
MDR-0281 | PRJ-007 | Vessel Mechanical Design | Mechanical | Q. Chukwu | 2 | 2026-07-10 | 2026-08-21 | Issued for Review | FALSE | In Review
MDR-0282 | PRJ-007 | Tie-in Schedule | Piping | E. Danjuma | 4 | 2026-09-24 | 2026-10-15 | Issued for Review | FALSE | In Review
MDR-0283 | PRJ-007 | Rotating Equipment Spec | Mechanical | A. Ihejirika | 3 | 2026-09-04 | 2026-10-12 | Internal Development | FALSE | In Progress
MDR-0284 | PRJ-007 | Instrument Datasheet | Instrumentation | S. Uzoma | 0 | 2026-09-09 | 2026-09-29 | Issued for Review | FALSE | In Review
MDR-0285 | PRJ-007 | Pipeline Route Survey - OML 4 | Pipeline | R. Balogun | 2 | 2026-08-27 | 2026-09-17 | Issued for Review | FALSE | In Review
MDR-0286 | PRJ-007 | Structural GA Drawing | Civil / Structural | T. Ogundele | 3 | 2026-08-14 | 2026-09-05 | Comments Received | FALSE | In Review
MDR-0287 | PRJ-007 | Process Flow Diagram - OML 4 | Process | S. Aliyu | 3 | 2026-09-02 | 2026-09-22 | Internal Development | FALSE | In Progress
MDR-0288 | PRJ-010 | Process Datasheet | Process | G. Chukwu | 1 | 2026-04-12 | 2026-05-04 | Approved / IFI | FALSE | Complete
MDR-0289 | PRJ-010 | Piping Specification | Piping | P. Ndukwe | 0 | 2026-07-01 | 2026-07-26 | Approved / IFI | FALSE | Complete
MDR-0290 | PRJ-010 | Electrical Design Basis - OML 5 | Electrical | F. Etim | 0 | 2026-03-02 | 2026-03-15 | Approved / IFI | FALSE | Complete
MDR-0291 | PRJ-010 | Piping Stress Report | Mechanical | A. Ihejirika | 4 | 2026-06-07 | 2026-07-06 | Approved / IFI | FALSE | Complete
MDR-0292 | PRJ-010 | Process Flow Diagram | Process | N. Effiong | 3 | 2026-03-20 | 2026-04-20 | Approved / IFI | FALSE | Complete
MDR-0293 | PRJ-010 | Process Simulation Report - OML 5 | Process | G. Chukwu | 3 | 2026-03-04 | 2026-03-25 | Approved / IFI | FALSE | Complete
MDR-0294 | PRJ-010 | Mechanical Handling Study | Mechanical | A. Ihejirika | 2 | 2026-02-04 | 2026-02-15 | Approved / IFI | FALSE | Complete
MDR-0295 | PRJ-010 | Loop Diagram - OML 5 | Instrumentation | I. Briggs | 2 | 2026-06-01 | 2026-06-24 | Approved / IFI | FALSE | Complete
MDR-0296 | PRJ-010 | Process Datasheet | Process | S. Aliyu | 0 | 2026-06-04 | 2026-06-27 | Approved / IFI | FALSE | Complete
MDR-0297 | PRJ-010 | Corrosion Assessment Report - OML 5 | Pipeline | R. Balogun | 2 | 2026-05-14 | 2026-05-27 | Approved / IFI | FALSE | Complete
MDR-0298 | PRJ-010 | Vessel Mechanical Design | Mechanical | B. Yusuf | 3 | 2026-09-04 | 2026-09-25 | Comments Received | FALSE | In Review
MDR-0299 | PRJ-010 | Line List | Piping | I. Ogundele | 2 | 2026-08-23 | 2026-09-21 | Comments Received | FALSE | In Review
MDR-0300 | PRJ-010 | Pipeline Design Basis | Pipeline | C. Ibrahim | 1 | 2026-08-13 | 2026-09-23 | Internal Development | FALSE | In Progress
MDR-0301 | PRJ-010 | Instrument Datasheet | Instrumentation | S. Uzoma | 1 | 2026-09-13 | 2026-10-22 | Revise & Resubmit | FALSE | Revise
MDR-0302 | PRJ-010 | Mechanical Handling Study | Mechanical | Q. Chukwu | 0 | 2026-07-19 | 2026-08-31 | Internal Development | FALSE | In Progress
MDR-0303 | PRJ-010 | Process Design Basis - OML 5 | Process | S. Aliyu | 2 | 2026-07-29 | 2026-08-26 | Issued for Review | FALSE | In Review
MDR-0304 | PRJ-010 | Compressor Datasheet | Mechanical | D. Umeh | 1 | 2026-08-23 | 2026-09-18 | Internal Development | FALSE | In Progress
MDR-0305 | PRJ-010 | Loop Diagram | Instrumentation | S. Aliyu | 4 | 2026-07-22 | 2026-08-30 | Issued for Review | FALSE | In Review
MDR-0306 | PRJ-010 | Relief & Blowdown Study | Process | J. Ibrahim | 2 | 2026-09-14 | 2026-10-08 | Comments Received | FALSE | In Review
MDR-0307 | PRJ-010 | Relief & Blowdown Study - OML 5 | Process | S. Aliyu | 2 | 2026-08-21 | 2026-09-25 | Issued for Review | FALSE | In Review
MDR-0308 | PRJ-014 | Load List | Electrical | C. James | 4 | 2026-03-17 | 2026-04-08 | Approved / IFI | FALSE | Complete
MDR-0309 | PRJ-014 | Pipeline Route Survey | Pipeline | C. Ibrahim | 3 | 2026-01-23 | 2026-03-02 | Approved / IFI | FALSE | Complete
MDR-0310 | PRJ-014 | Instrument Datasheet | Instrumentation | I. Briggs | 0 | 2026-02-28 | 2026-03-12 | Approved / IFI | FALSE | Complete
MDR-0311 | PRJ-014 | Instrument Datasheet | Instrumentation | I. Briggs | 1 | 2026-05-29 | 2026-07-06 | Approved / IFI | FALSE | Complete
MDR-0312 | PRJ-014 | Pipe Support Register | Piping | E. Danjuma | 3 | 2026-06-17 | 2026-07-18 | Approved / IFI | FALSE | Complete
MDR-0313 | PRJ-014 | P&ID | Process | J. Musa | 4 | 2026-06-02 | 2026-07-02 | Approved / IFI | FALSE | Complete
MDR-0314 | PRJ-014 | Corrosion Assessment Report | Pipeline | C. Ibrahim | 4 | 2026-02-03 | 2026-03-11 | Approved / IFI | FALSE | Complete
MDR-0315 | PRJ-014 | Steelwork Fabrication Drawing | Civil / Structural | T. Ogundele | 3 | 2026-03-16 | 2026-04-21 | Approved / IFI | FALSE | Complete
MDR-0316 | PRJ-014 | Single Line Diagram | Electrical | R. Ogunleye | 3 | 2026-05-09 | 2026-06-04 | Approved / IFI | FALSE | Complete
MDR-0317 | PRJ-014 | Cable Schedule | Electrical | F. Etim | 1 | 2026-03-17 | 2026-04-01 | Approved / IFI | FALSE | Complete
MDR-0318 | PRJ-014 | Cable Schedule - OML 6 | Electrical | C. James | 3 | 2026-01-19 | 2026-02-02 | Approved / IFI | FALSE | Complete
MDR-0319 | PRJ-014 | Lifting Plan | Mechanical | A. Ihejirika | 0 | 2026-08-02 | 2026-09-05 | Internal Development | FALSE | In Progress
MDR-0320 | PRJ-014 | P&ID | Process | J. Musa | 0 | 2026-08-06 | 2026-09-14 | Issued for Review | FALSE | In Review
MDR-0321 | PRJ-014 | Lifting Plan - OML 6 | Mechanical | Q. Chukwu | 2 | 2026-08-03 | 2026-09-07 | Internal Development | FALSE | In Progress
MDR-0322 | PRJ-014 | Relief & Blowdown Study | Process | A. Musa | 0 | 2026-09-01 | 2026-09-23 | Comments Received | FALSE | In Review
MDR-0323 | PRJ-014 | Instrument Datasheet - OML 6 | Instrumentation | S. Uzoma | 1 | 2026-08-16 | 2026-09-20 | Issued for Review | FALSE | In Review
MDR-0324 | PRJ-014 | Motor Datasheet | Electrical | R. Ogunleye | 4 | 2026-08-08 | 2026-08-28 | Issued for Review | FALSE | In Review
MDR-0325 | PRJ-020 | Rotating Equipment Spec - OML 8 | Mechanical | A. Ihejirika | 1 | 2026-01-15 | 2026-02-19 | Approved / IFI | FALSE | Complete
MDR-0326 | PRJ-020 | Compressor Datasheet | Mechanical | B. Okafor | 3 | 2026-02-09 | 2026-03-20 | Approved / IFI | FALSE | Complete
MDR-0327 | PRJ-020 | Tie-in Schedule - OML 8 | Piping | I. Ogundele | 4 | 2026-06-16 | 2026-06-27 | Approved / IFI | FALSE | Complete
MDR-0328 | PRJ-020 | Electrical Design Basis | Electrical | R. Ogunleye | 2 | 2026-04-06 | 2026-05-06 | Approved / IFI | FALSE | Complete
MDR-0329 | PRJ-020 | HAZOP Report | Process | J. Ibrahim | 0 | 2026-04-14 | 2026-05-19 | Approved / IFI | FALSE | Complete
MDR-0330 | PRJ-020 | Foundation Design Report | Civil / Structural | T. Ogundele | 3 | 2026-03-02 | 2026-04-02 | Approved / IFI | FALSE | Complete
MDR-0331 | PRJ-020 | Pipe Support Register - OML 8 | Piping | P. Ndukwe | 3 | 2026-04-27 | 2026-05-25 | Approved / IFI | FALSE | Complete
MDR-0332 | PRJ-020 | Rotating Equipment Spec - OML 8 | Mechanical | Q. Chukwu | 0 | 2026-05-22 | 2026-06-04 | Approved / IFI | FALSE | Complete
MDR-0333 | PRJ-020 | Piping Stress Report | Mechanical | B. Okafor | 3 | 2026-08-27 | 2026-10-08 | Comments Received | FALSE | In Review
MDR-0334 | PRJ-020 | Cable Schedule | Electrical | F. Etim | 4 | 2026-09-10 | 2026-10-20 | Revise & Resubmit | FALSE | Revise
MDR-0335 | PRJ-020 | Heat & Material Balance | Process | A. Musa | 2 | 2026-10-06 | 2026-10-25 | Internal Development | FALSE | In Progress
MDR-0336 | PRJ-020 | Piping Stress Report | Mechanical | A. Ihejirika | 3 | 2026-07-22 | 2026-08-23 | Issued for Review | FALSE | In Review
MDR-0337 | PRJ-020 | Loop Diagram - OML 8 | Instrumentation | H. Sanni | 3 | 2026-09-14 | 2026-10-20 | Comments Received | FALSE | In Review
MDR-0338 | PRJ-020 | Tie-in Schedule | Piping | E. Okoro | 4 | 2026-07-12 | 2026-08-22 | Issued for Review | FALSE | In Review
MDR-0339 | PRJ-020 | Lifting Plan | Mechanical | A. Ihejirika | 2 | 2026-07-25 | 2026-09-07 | Internal Development | FALSE | In Progress
MDR-0340 | PRJ-020 | Piping Specification | Piping | U. Chukwuemeka | 0 | 2026-07-12 | 2026-08-18 | Internal Development | FALSE | In Progress
MDR-0341 | PRJ-020 | Steelwork Fabrication Drawing | Civil / Structural | M. Yakubu | 4 | 2026-08-16 | 2026-09-28 | Issued for Review | FALSE | In Review
MDR-0342 | PRJ-020 | Instrument Datasheet - OML 8 | Instrumentation | S. Aliyu | 1 | 2026-09-02 | 2026-10-09 | Issued for Review | FALSE | In Review
MDR-0343 | PRJ-020 | Process Design Basis | Process | N. Effiong | 3 | 2026-07-20 | 2026-08-29 | Internal Development | FALSE | In Progress
MDR-0344 | PRJ-020 | Line List | Piping | I. Ogundele | 3 | 2026-08-22 | 2026-09-09 | Issued for Review | FALSE | In Review
MDR-0345 | GLB-005 | Lifting Plan - Global | Mechanical | D. Umeh | 0 | 2026-01-07 | 2026-02-04 | Approved / IFI | FALSE | Complete
MDR-0346 | GLB-005 | Compressor Datasheet - Global | Mechanical | B. Okafor | 4 | 2026-02-06 | 2026-02-18 | Approved / IFI | FALSE | Complete
MDR-0347 | GLB-005 | Instrument Index - Global | Instrumentation | I. Briggs | 0 | 2026-02-05 | 2026-02-24 | Approved / IFI | FALSE | Complete
MDR-0348 | GLB-005 | Vessel Mechanical Design | Mechanical | B. Okafor | 0 | 2026-07-25 | 2026-08-04 | Approved / IFI | FALSE | Complete
MDR-0349 | GLB-005 | Line List - Global | Piping | E. Okoro | 2 | 2026-04-13 | 2026-05-14 | Approved / IFI | FALSE | Complete
MDR-0350 | GLB-005 | Mechanical Handling Study | Mechanical | D. Umeh | 3 | 2026-06-05 | 2026-06-17 | Approved / IFI | FALSE | Complete
MDR-0351 | GLB-005 | Lifting Plan - Global | Mechanical | Q. Chukwu | 0 | 2026-04-08 | 2026-04-27 | Approved / IFI | FALSE | Complete
MDR-0352 | GLB-005 | P&ID | Process | G. Chukwu | 0 | 2026-01-02 | 2026-02-10 | Approved / IFI | FALSE | Complete
MDR-0353 | GLB-005 | Mechanical Handling Study - Global | Mechanical | D. Umeh | 3 | 2026-06-13 | 2026-07-19 | Approved / IFI | FALSE | Complete
MDR-0354 | GLB-005 | Process Design Basis | Process | N. Effiong | 0 | 2026-02-15 | 2026-03-25 | Approved / IFI | FALSE | Complete
MDR-0355 | GLB-005 | Steelwork Fabrication Drawing | Civil / Structural | T. Ogundele | 0 | 2026-07-24 | 2026-08-27 | Internal Development | FALSE | In Progress
MDR-0356 | GLB-005 | Pump Datasheet | Mechanical | Q. Chukwu | 4 | 2026-09-04 | 2026-09-27 | Internal Development | FALSE | In Progress
MDR-0357 | GLB-005 | Line List | Piping | I. Ogundele | 4 | 2026-09-28 | 2026-10-27 | Issued for Review | FALSE | In Review
MDR-0358 | GLB-005 | Steelwork Fabrication Drawing - Global | Civil / Structural | N. Uzoma | 2 | 2026-07-18 | 2026-08-19 | Issued for Review | FALSE | In Review
MDR-0359 | GLB-005 | Process Simulation Report - Global | Process | J. Ibrahim | 3 | 2026-09-05 | 2026-10-08 | Issued for Review | FALSE | In Review
MDR-0360 | GLB-005 | Process Datasheet | Process | J. Musa | 4 | 2026-08-22 | 2026-09-14 | Internal Development | FALSE | In Progress
MDR-0361 | GLB-005 | Cause & Effect Diagram | Instrumentation | H. Sanni | 4 | 2026-09-10 | 2026-10-23 | Internal Development | FALSE | In Progress
MDR-0362 | GLB-005 | Heat & Material Balance | Process | G. Chukwu | 0 | 2026-08-28 | 2026-09-28 | Internal Development | FALSE | In Progress
MDR-0363 | GLB-005 | Lifting Plan | Mechanical | B. Okafor | 1 | 2026-08-19 | 2026-09-10 | Issued for Review | FALSE | In Review
MDR-0364 | GLB-005 | Tie-in Schedule - Global | Piping | E. Danjuma | 4 | 2026-08-02 | 2026-08-21 | Revise & Resubmit | FALSE | Revise
MDR-0365 | GLB-005 | HAZOP Report - Global | Process | S. Aliyu | 4 | 2026-09-10 | 2026-10-15 | Issued for Review | FALSE | In Review
MDR-0366 | GLB-005 | Pipe Support Register | Piping | E. Okoro | 2 | 2026-08-05 | 2026-08-30 | Internal Development | FALSE | In Progress
MDR-0367 | PRJ-004 | Lifting Plan | Mechanical | D. Umeh | 2 | 2026-06-19 | 2026-07-12 | Approved / IFI | FALSE | Complete
MDR-0368 | PRJ-004 | Piping GA Drawing | Piping | U. Chukwuemeka | 4 | 2026-07-05 | 2026-08-04 | Approved / IFI | FALSE | Complete
MDR-0369 | PRJ-004 | Motor Datasheet | Electrical | C. James | 3 | 2026-01-13 | 2026-02-18 | Approved / IFI | FALSE | Complete
MDR-0370 | PRJ-004 | Vessel Mechanical Design | Mechanical | B. Okafor | 2 | 2026-06-17 | 2026-07-15 | Approved / IFI | FALSE | Complete
MDR-0371 | PRJ-004 | Equipment Datasheet | Mechanical | B. Yusuf | 2 | 2026-03-31 | 2026-04-14 | Approved / IFI | FALSE | Complete
MDR-0372 | PRJ-004 | Piping Isometric | Piping | U. Chukwuemeka | 4 | 2026-05-01 | 2026-05-20 | Approved / IFI | FALSE | Complete
MDR-0373 | PRJ-004 | Piping Stress Report | Mechanical | A. Ihejirika | 1 | 2026-05-20 | 2026-06-10 | Approved / IFI | FALSE | Complete
MDR-0374 | PRJ-004 | Compressor Datasheet | Mechanical | D. Umeh | 4 | 2026-05-03 | 2026-05-13 | Approved / IFI | FALSE | Complete
MDR-0375 | PRJ-004 | Process Simulation Report - OML 1 | Process | G. Chukwu | 2 | 2026-07-02 | 2026-07-21 | Approved / IFI | FALSE | Complete
MDR-0376 | PRJ-004 | Equipment Datasheet | Mechanical | D. Umeh | 4 | 2026-04-06 | 2026-05-01 | Approved / IFI | FALSE | Complete
MDR-0377 | PRJ-004 | Lifting Plan - OML 1 | Mechanical | A. Ihejirika | 4 | 2026-01-23 | 2026-02-11 | Approved / IFI | FALSE | Complete
MDR-0378 | PRJ-004 | Process Simulation Report | Process | J. Ibrahim | 0 | 2026-05-20 | 2026-06-22 | Approved / IFI | FALSE | Complete
MDR-0379 | PRJ-004 | Piping GA Drawing - OML 1 | Piping | E. Danjuma | 4 | 2026-04-24 | 2026-05-16 | Approved / IFI | FALSE | Complete
MDR-0380 | PRJ-004 | Relief & Blowdown Study - OML 1 | Process | G. Chukwu | 3 | 2026-06-22 | 2026-07-26 | Approved / IFI | FALSE | Complete
MDR-0381 | PRJ-004 | Process Simulation Report | Process | A. Musa | 2 | 2026-01-03 | 2026-02-06 | Approved / IFI | FALSE | Complete
MDR-0382 | PRJ-004 | Heat & Material Balance | Process | S. Aliyu | 1 | 2026-02-02 | 2026-03-01 | Approved / IFI | FALSE | Complete
MDR-0383 | PRJ-004 | Lifting Plan | Mechanical | B. Yusuf | 3 | 2026-10-06 | 2026-10-24 | Issued for Review | FALSE | In Review
MDR-0384 | PRJ-004 | Control Narrative | Instrumentation | I. Briggs | 2 | 2026-08-12 | 2026-08-30 | Internal Development | FALSE | In Progress
MDR-0385 | PRJ-004 | P&ID | Process | N. Effiong | 3 | 2026-07-18 | 2026-08-23 | Issued for Review | FALSE | In Review
MDR-0386 | PRJ-004 | Single Line Diagram | Electrical | F. Etim | 2 | 2026-08-14 | 2026-09-07 | Comments Received | FALSE | In Review
MDR-0387 | PRJ-004 | Line List | Piping | U. Chukwuemeka | 1 | 2026-09-09 | 2026-10-08 | Issued for Review | FALSE | In Review
MDR-0388 | PRJ-012 | Process Datasheet | Process | G. Chukwu | 4 | 2026-03-08 | 2026-04-13 | Approved / IFI | FALSE | Complete
MDR-0389 | PRJ-012 | HAZOP Report - OML 4 | Process | A. Musa | 3 | 2026-03-11 | 2026-04-11 | Approved / IFI | FALSE | Complete
MDR-0390 | PRJ-012 | Process Flow Diagram - OML 4 | Process | J. Ibrahim | 2 | 2026-05-29 | 2026-06-14 | Approved / IFI | FALSE | Complete
MDR-0391 | PRJ-012 | Process Flow Diagram | Process | J. Ibrahim | 0 | 2026-06-25 | 2026-07-30 | Approved / IFI | FALSE | Complete
MDR-0392 | PRJ-012 | P&ID | Process | N. Effiong | 3 | 2026-01-18 | 2026-02-09 | Approved / IFI | FALSE | Complete
MDR-0393 | PRJ-012 | Equipment Datasheet | Mechanical | Q. Chukwu | 0 | 2026-05-10 | 2026-06-03 | Approved / IFI | FALSE | Complete
MDR-0394 | PRJ-012 | Process Datasheet | Process | N. Effiong | 1 | 2026-02-01 | 2026-02-17 | Approved / IFI | FALSE | Complete
MDR-0395 | PRJ-012 | Cause & Effect Diagram | Instrumentation | S. Aliyu | 0 | 2026-05-27 | 2026-07-05 | Approved / IFI | FALSE | Complete
MDR-0396 | PRJ-012 | Pump Datasheet | Mechanical | Q. Chukwu | 0 | 2026-04-11 | 2026-05-03 | Approved / IFI | FALSE | Complete
MDR-0397 | PRJ-012 | SCADA Architecture Drawing | Instrumentation | S. Aliyu | 4 | 2026-04-10 | 2026-04-27 | Approved / IFI | FALSE | Complete
MDR-0398 | PRJ-012 | Vessel Mechanical Design | Mechanical | B. Okafor | 3 | 2026-02-02 | 2026-03-04 | Approved / IFI | FALSE | Complete
MDR-0399 | PRJ-012 | Steelwork Fabrication Drawing - OML 4 | Civil / Structural | T. Ogundele | 4 | 2025-12-31 | 2026-01-30 | Approved / IFI | FALSE | Complete
MDR-0400 | PRJ-012 | Instrument Index - OML 4 | Instrumentation | S. Aliyu | 2 | 2026-05-08 | 2026-06-04 | Approved / IFI | FALSE | Complete
MDR-0401 | PRJ-012 | Load List | Electrical | M. Ekong | 1 | 2026-05-27 | 2026-06-18 | Approved / IFI | FALSE | Complete
MDR-0402 | PRJ-012 | Tie-in Schedule | Piping | U. Chukwuemeka | 2 | 2026-02-23 | 2026-03-19 | Approved / IFI | FALSE | Complete
MDR-0403 | PRJ-012 | SCADA Architecture Drawing - OML 4 | Instrumentation | S. Uzoma | 1 | 2026-04-23 | 2026-05-29 | Approved / IFI | FALSE | Complete
MDR-0404 | PRJ-012 | Heat & Material Balance | Process | S. Aliyu | 2 | 2026-02-10 | 2026-02-22 | Approved / IFI | FALSE | Complete
MDR-0405 | PRJ-012 | Pump Datasheet - OML 4 | Mechanical | B. Yusuf | 2 | 2026-05-10 | 2026-06-12 | Approved / IFI | FALSE | Complete
MDR-0406 | PRJ-012 | Cause & Effect Diagram | Instrumentation | H. Sanni | 1 | 2026-06-16 | 2026-06-30 | Approved / IFI | FALSE | Complete
MDR-0407 | PRJ-012 | Instrument Datasheet - OML 4 | Instrumentation | S. Aliyu | 1 | 2026-04-06 | 2026-05-15 | Approved / IFI | FALSE | Complete
MDR-0408 | PRJ-012 | Foundation Design Report - OML 4 | Civil / Structural | N. Uzoma | 3 | 2026-04-09 | 2026-05-14 | Approved / IFI | FALSE | Complete
MDR-0409 | PRJ-012 | Tie-in Schedule - OML 4 | Piping | U. Chukwuemeka | 4 | 2026-06-19 | 2026-07-08 | Approved / IFI | FALSE | Complete
MDR-0410 | PRJ-012 | Instrument Datasheet | Instrumentation | S. Uzoma | 0 | 2025-12-24 | 2026-01-31 | Approved / IFI | FALSE | Complete
MDR-0411 | PRJ-012 | Steelwork Fabrication Drawing - OML 4 | Civil / Structural | M. Yakubu | 4 | 2026-07-21 | 2026-08-30 | Issued for Review | FALSE | In Review
MDR-0412 | PRJ-012 | Vessel Mechanical Design | Mechanical | B. Okafor | 2 | 2026-09-09 | 2026-10-04 | Revise & Resubmit | FALSE | Revise
MDR-0413 | PRJ-012 | Cause & Effect Diagram | Instrumentation | H. Sanni | 2 | 2026-09-01 | 2026-10-13 | Issued for Review | FALSE | In Review
MDR-0414 | PRJ-016 | Control Narrative | Instrumentation | S. Uzoma | 3 | 2026-03-03 | 2026-03-29 | Approved / IFI | FALSE | Complete
MDR-0415 | PRJ-016 | Process Simulation Report | Process | S. Aliyu | 1 | 2026-02-04 | 2026-03-15 | Approved / IFI | FALSE | Complete
MDR-0416 | PRJ-016 | Mechanical Handling Study | Mechanical | Q. Chukwu | 3 | 2026-02-15 | 2026-02-26 | Approved / IFI | FALSE | Complete
MDR-0417 | PRJ-016 | Vessel Mechanical Design | Mechanical | B. Yusuf | 2 | 2026-02-07 | 2026-02-23 | Approved / IFI | FALSE | Complete
MDR-0418 | PRJ-016 | Process Flow Diagram | Process | J. Musa | 1 | 2026-06-05 | 2026-06-24 | Approved / IFI | FALSE | Complete
MDR-0419 | PRJ-016 | Loop Diagram | Instrumentation | I. Briggs | 2 | 2026-04-26 | 2026-05-20 | Approved / IFI | FALSE | Complete
MDR-0420 | PRJ-016 | Piping Isometric | Piping | P. Ndukwe | 4 | 2026-05-08 | 2026-06-04 | Approved / IFI | FALSE | Complete
MDR-0421 | PRJ-016 | Instrument Index | Instrumentation | I. Briggs | 2 | 2026-05-07 | 2026-06-14 | Approved / IFI | FALSE | Complete
MDR-0422 | PRJ-016 | Process Datasheet - OML 7 | Process | J. Ibrahim | 0 | 2026-07-10 | 2026-07-31 | Approved / IFI | FALSE | Complete
MDR-0423 | PRJ-016 | Single Line Diagram | Electrical | C. James | 2 | 2026-04-12 | 2026-05-10 | Approved / IFI | FALSE | Complete
MDR-0424 | PRJ-016 | Tie-in Schedule | Piping | I. Ogundele | 2 | 2026-03-26 | 2026-04-17 | Approved / IFI | FALSE | Complete
MDR-0425 | PRJ-016 | Pipe Support Register - OML 7 | Piping | I. Ogundele | 3 | 2026-05-19 | 2026-06-01 | Approved / IFI | FALSE | Complete
MDR-0426 | PRJ-016 | Relief & Blowdown Study | Process | N. Effiong | 0 | 2026-01-22 | 2026-02-04 | Approved / IFI | FALSE | Complete
MDR-0427 | PRJ-016 | Compressor Datasheet | Mechanical | Q. Chukwu | 0 | 2026-09-20 | 2026-10-26 | Issued for Review | FALSE | In Review
MDR-0428 | PRJ-016 | Piping Stress Report | Mechanical | A. Ihejirika | 1 | 2026-09-05 | 2026-10-12 | Issued for Review | FALSE | In Review
MDR-0429 | PRJ-016 | Piping Isometric | Piping | E. Danjuma | 1 | 2026-08-16 | 2026-09-14 | Internal Development | FALSE | In Progress
MDR-0430 | PRJ-016 | Piping Isometric | Piping | E. Danjuma | 1 | 2026-08-22 | 2026-09-20 | Comments Received | FALSE | In Review
MDR-0431 | PRJ-016 | Vessel Mechanical Design | Mechanical | B. Okafor | 0 | 2026-09-08 | 2026-10-11 | Issued for Review | FALSE | In Review
MDR-0432 | PRJ-016 | Mechanical Handling Study | Mechanical | B. Okafor | 0 | 2026-09-20 | 2026-10-21 | Issued for Review | FALSE | In Review
MDR-0433 | PRJ-016 | Line List | Piping | I. Ogundele | 2 | 2026-07-23 | 2026-08-22 | Revise & Resubmit | FALSE | Revise
MDR-0434 | PRJ-016 | HAZOP Report | Process | J. Ibrahim | 0 | 2026-10-09 | 2026-10-24 | Comments Received | FALSE | In Review
MDR-0435 | PRJ-022 | Instrument Index | Instrumentation | S. Aliyu | 0 | 2026-05-17 | 2026-06-03 | Approved / IFI | FALSE | Complete
MDR-0436 | PRJ-022 | Piping Specification - OML 9 | Piping | E. Danjuma | 4 | 2026-06-02 | 2026-06-20 | Approved / IFI | FALSE | Complete
MDR-0437 | PRJ-022 | Process Datasheet | Process | S. Aliyu | 1 | 2026-03-24 | 2026-04-28 | Approved / IFI | FALSE | Complete
MDR-0438 | PRJ-022 | Lifting Plan - OML 9 | Mechanical | Q. Chukwu | 4 | 2026-05-16 | 2026-06-10 | Approved / IFI | FALSE | Complete
MDR-0439 | PRJ-022 | Piping Specification - OML 9 | Piping | I. Ogundele | 0 | 2026-05-09 | 2026-06-05 | Approved / IFI | FALSE | Complete
MDR-0440 | PRJ-022 | Cause & Effect Diagram | Instrumentation | I. Briggs | 4 | 2026-02-14 | 2026-03-24 | Approved / IFI | FALSE | Complete
MDR-0441 | PRJ-022 | Vessel Mechanical Design | Mechanical | B. Yusuf | 0 | 2026-05-12 | 2026-06-19 | Approved / IFI | FALSE | Complete
MDR-0442 | PRJ-022 | P&ID - OML 9 | Process | S. Aliyu | 2 | 2026-05-03 | 2026-05-21 | Approved / IFI | FALSE | Complete
MDR-0443 | PRJ-022 | SCADA Architecture Drawing | Instrumentation | H. Sanni | 2 | 2026-06-14 | 2026-07-23 | Approved / IFI | FALSE | Complete
MDR-0444 | PRJ-022 | Line List | Piping | I. Ogundele | 4 | 2026-03-13 | 2026-03-30 | Approved / IFI | FALSE | Complete
MDR-0445 | PRJ-022 | Single Line Diagram | Electrical | M. Ekong | 2 | 2026-06-11 | 2026-07-17 | Approved / IFI | FALSE | Complete
MDR-0446 | PRJ-022 | Instrument Datasheet - OML 9 | Instrumentation | H. Sanni | 2 | 2026-04-09 | 2026-04-28 | Approved / IFI | FALSE | Complete
MDR-0447 | PRJ-022 | Process Simulation Report - OML 9 | Process | G. Chukwu | 1 | 2026-06-08 | 2026-07-03 | Approved / IFI | FALSE | Complete
MDR-0448 | PRJ-022 | Process Design Basis | Process | N. Effiong | 4 | 2026-05-29 | 2026-06-18 | Approved / IFI | FALSE | Complete
MDR-0449 | PRJ-022 | Rotating Equipment Spec | Mechanical | Q. Chukwu | 4 | 2026-03-25 | 2026-04-29 | Approved / IFI | FALSE | Complete
MDR-0450 | PRJ-022 | Lifting Plan | Mechanical | Q. Chukwu | 3 | 2026-05-25 | 2026-06-14 | Approved / IFI | FALSE | Complete
MDR-0451 | PRJ-022 | Instrument Datasheet | Instrumentation | S. Uzoma | 3 | 2026-08-02 | 2026-09-03 | Issued for Review | FALSE | In Review
MDR-0452 | PRJ-022 | Geotechnical Report | Civil / Structural | T. Ogundele | 1 | 2026-08-11 | 2026-09-02 | Issued for Review | FALSE | In Review
MDR-0453 | PRJ-022 | Geotechnical Report | Civil / Structural | M. Yakubu | 3 | 2026-09-21 | 2026-10-12 | Issued for Review | FALSE | In Review
MDR-0454 | PRJ-022 | Process Simulation Report | Process | G. Chukwu | 3 | 2026-08-18 | 2026-09-04 | Revise & Resubmit | FALSE | Revise
MDR-0455 | PRJ-022 | Line List | Piping | U. Chukwuemeka | 1 | 2026-09-24 | 2026-10-17 | Revise & Resubmit | FALSE | Revise
MDR-0456 | PRJ-026 | Single Line Diagram - OML 10 | Electrical | F. Etim | 2 | 2026-01-19 | 2026-02-01 | Approved / IFI | FALSE | Complete
MDR-0457 | PRJ-026 | Electrical Design Basis | Electrical | R. Ogunleye | 0 | 2026-04-27 | 2026-05-31 | Approved / IFI | FALSE | Complete
MDR-0458 | PRJ-026 | Piping Specification - OML 10 | Piping | I. Ogundele | 2 | 2026-06-05 | 2026-06-19 | Approved / IFI | FALSE | Complete
MDR-0459 | PRJ-026 | HAZOP Report | Process | J. Musa | 1 | 2026-05-23 | 2026-06-14 | Approved / IFI | FALSE | Complete
MDR-0460 | PRJ-026 | Piping Stress Report | Mechanical | A. Ihejirika | 4 | 2026-07-23 | 2026-08-09 | Approved / IFI | FALSE | Complete
MDR-0461 | PRJ-026 | Line List - OML 10 | Piping | P. Ndukwe | 2 | 2026-03-28 | 2026-05-04 | Approved / IFI | FALSE | Complete
MDR-0462 | PRJ-026 | Vessel Mechanical Design - OML 10 | Mechanical | D. Umeh | 3 | 2026-03-12 | 2026-04-19 | Approved / IFI | FALSE | Complete
MDR-0463 | PRJ-026 | Vessel Mechanical Design | Mechanical | B. Okafor | 4 | 2026-05-21 | 2026-06-19 | Approved / IFI | FALSE | Complete
MDR-0464 | PRJ-026 | Steelwork Fabrication Drawing - OML 10 | Civil / Structural | N. Uzoma | 0 | 2026-06-23 | 2026-07-28 | Approved / IFI | FALSE | Complete
MDR-0465 | PRJ-026 | Material Take-Off | Piping | P. Ndukwe | 4 | 2026-07-05 | 2026-08-03 | Approved / IFI | FALSE | Complete
MDR-0466 | PRJ-026 | Piping Isometric | Piping | E. Danjuma | 3 | 2026-06-18 | 2026-07-21 | Approved / IFI | FALSE | Complete
MDR-0467 | PRJ-026 | Single Line Diagram | Electrical | R. Ogunleye | 2 | 2026-06-16 | 2026-07-09 | Approved / IFI | FALSE | Complete
MDR-0468 | PRJ-026 | Pigging Study | Pipeline | C. Ibrahim | 3 | 2026-05-01 | 2026-06-08 | Approved / IFI | FALSE | Complete
MDR-0469 | PRJ-026 | HAZOP Report - OML 10 | Process | J. Musa | 0 | 2026-03-01 | 2026-03-31 | Approved / IFI | FALSE | Complete
MDR-0470 | PRJ-026 | Relief & Blowdown Study - OML 10 | Process | J. Musa | 2 | 2026-08-06 | 2026-08-26 | Revise & Resubmit | FALSE | Revise
MDR-0471 | PRJ-026 | Line List | Piping | U. Chukwuemeka | 1 | 2026-09-01 | 2026-10-05 | Revise & Resubmit | FALSE | Revise
MDR-0472 | PRJ-026 | Corrosion Assessment Report | Pipeline | C. Ibrahim | 1 | 2026-08-13 | 2026-09-22 | Issued for Review | FALSE | In Review
MDR-0473 | PRJ-017 | Rotating Equipment Spec | Mechanical | B. Okafor | 3 | 2026-03-12 | 2026-03-27 | Approved / IFI | FALSE | Complete
MDR-0474 | PRJ-017 | Earthing Layout | Electrical | F. Etim | 2 | 2026-01-08 | 2026-01-29 | Approved / IFI | FALSE | Complete
MDR-0475 | PRJ-017 | Heat & Material Balance | Process | A. Musa | 0 | 2026-04-28 | 2026-05-11 | Approved / IFI | FALSE | Complete
MDR-0476 | PRJ-017 | Tie-in Schedule | Piping | P. Ndukwe | 0 | 2026-02-08 | 2026-02-26 | Approved / IFI | FALSE | Complete
MDR-0477 | PRJ-017 | Vessel Mechanical Design - OML 7 | Mechanical | D. Umeh | 0 | 2026-04-30 | 2026-05-22 | Approved / IFI | FALSE | Complete
MDR-0478 | PRJ-017 | Pump Datasheet - OML 7 | Mechanical | D. Umeh | 0 | 2026-01-04 | 2026-01-30 | Approved / IFI | FALSE | Complete
MDR-0479 | PRJ-017 | Process Datasheet - OML 7 | Process | S. Aliyu | 2 | 2026-03-04 | 2026-03-21 | Approved / IFI | FALSE | Complete
MDR-0480 | PRJ-017 | Pipeline Design Basis - OML 7 | Pipeline | R. Balogun | 2 | 2026-04-22 | 2026-05-09 | Approved / IFI | FALSE | Complete
MDR-0481 | PRJ-017 | Single Line Diagram | Electrical | M. Ekong | 0 | 2026-04-30 | 2026-05-11 | Approved / IFI | FALSE | Complete
MDR-0482 | PRJ-017 | Rotating Equipment Spec | Mechanical | D. Umeh | 1 | 2026-01-31 | 2026-02-14 | Approved / IFI | FALSE | Complete
MDR-0483 | PRJ-017 | Equipment Datasheet - OML 7 | Mechanical | D. Umeh | 4 | 2026-06-20 | 2026-07-21 | Approved / IFI | FALSE | Complete
MDR-0484 | PRJ-017 | Pigging Study - OML 7 | Pipeline | R. Balogun | 4 | 2026-01-11 | 2026-02-17 | Approved / IFI | FALSE | Complete
MDR-0485 | PRJ-017 | Mechanical Handling Study | Mechanical | D. Umeh | 0 | 2026-04-05 | 2026-04-23 | Approved / IFI | FALSE | Complete
MDR-0486 | PRJ-017 | Line List | Piping | P. Ndukwe | 1 | 2026-03-10 | 2026-04-09 | Approved / IFI | FALSE | Complete
MDR-0487 | PRJ-017 | Loop Diagram - OML 7 | Instrumentation | H. Sanni | 2 | 2026-02-02 | 2026-02-21 | Approved / IFI | FALSE | Complete
MDR-0488 | PRJ-017 | Structural GA Drawing | Civil / Structural | N. Uzoma | 1 | 2026-07-02 | 2026-07-16 | Approved / IFI | FALSE | Complete
MDR-0489 | PRJ-017 | Relief & Blowdown Study | Process | J. Ibrahim | 1 | 2026-05-20 | 2026-06-09 | Approved / IFI | FALSE | Complete
MDR-0490 | PRJ-027 | Single Line Diagram | Electrical | R. Ogunleye | 0 | 2026-03-10 | 2026-04-03 | Approved / IFI | FALSE | Complete
MDR-0491 | PRJ-027 | Tie-in Schedule | Piping | E. Danjuma | 4 | 2026-04-07 | 2026-05-14 | Approved / IFI | FALSE | Complete
MDR-0492 | PRJ-027 | Cause & Effect Diagram | Instrumentation | I. Briggs | 2 | 2026-05-06 | 2026-05-26 | Approved / IFI | FALSE | Complete
MDR-0493 | PRJ-027 | Pump Datasheet | Mechanical | Q. Chukwu | 0 | 2026-05-19 | 2026-06-02 | Approved / IFI | FALSE | Complete
MDR-0494 | PRJ-027 | Foundation Design Report | Civil / Structural | T. Ogundele | 2 | 2026-06-18 | 2026-07-12 | Approved / IFI | FALSE | Complete
MDR-0495 | PRJ-027 | Cable Schedule - OML 2 | Electrical | M. Ekong | 3 | 2026-04-16 | 2026-05-22 | Approved / IFI | FALSE | Complete
MDR-0496 | PRJ-027 | Instrument Datasheet | Instrumentation | H. Sanni | 3 | 2026-01-25 | 2026-02-09 | Approved / IFI | FALSE | Complete
MDR-0497 | PRJ-027 | Process Datasheet - OML 2 | Process | S. Aliyu | 4 | 2026-05-01 | 2026-05-17 | Approved / IFI | FALSE | Complete
MDR-0498 | PRJ-027 | Heat & Material Balance | Process | A. Musa | 0 | 2026-05-27 | 2026-06-25 | Approved / IFI | FALSE | Complete
MDR-0499 | PRJ-027 | Vessel Mechanical Design - OML 2 | Mechanical | Q. Chukwu | 0 | 2026-01-29 | 2026-03-08 | Approved / IFI | FALSE | Complete
MDR-0500 | PRJ-027 | Relief & Blowdown Study | Process | S. Aliyu | 0 | 2026-02-09 | 2026-03-02 | Approved / IFI | FALSE | Complete
MDR-0501 | PRJ-027 | Material Take-Off | Piping | I. Ogundele | 0 | 2026-04-26 | 2026-05-15 | Approved / IFI | FALSE | Complete
MDR-0502 | PRJ-027 | Process Datasheet | Process | A. Musa | 3 | 2026-06-30 | 2026-07-12 | Approved / IFI | FALSE | Complete
MDR-0503 | PRJ-027 | Piping GA Drawing - OML 2 | Piping | U. Chukwuemeka | 4 | 2026-04-03 | 2026-04-29 | Approved / IFI | FALSE | Complete
MDR-0504 | PRJ-027 | Earthing Layout | Electrical | F. Etim | 2 | 2026-05-29 | 2026-06-20 | Approved / IFI | FALSE | Complete
MDR-0505 | PRJ-027 | Process Datasheet | Process | S. Aliyu | 0 | 2026-01-15 | 2026-02-23 | Approved / IFI | FALSE | Complete
MDR-0506 | PRJ-027 | Loop Diagram | Instrumentation | I. Briggs | 0 | 2026-06-10 | 2026-07-01 | Approved / IFI | FALSE | Complete
MDR-0507 | PRJ-027 | Loop Diagram | Instrumentation | S. Aliyu | 0 | 2026-05-22 | 2026-06-07 | Approved / IFI | FALSE | Complete
MDR-0508 | PRJ-027 | P&ID | Process | J. Musa | 0 | 2026-05-25 | 2026-06-28 | Approved / IFI | FALSE | Complete
MDR-0509 | PRJ-027 | Heat & Material Balance | Process | G. Chukwu | 2 | 2026-03-23 | 2026-04-12 | Approved / IFI | FALSE | Complete
MDR-0510 | PRJ-027 | Corrosion Assessment Report - OML 2 | Pipeline | R. Balogun | 1 | 2026-08-27 | 2026-09-30 | Issued for Review | FALSE | In Review
MDR-0511 | PRJ-028 | Process Simulation Report | Process | N. Effiong | 1 | 2026-03-21 | 2026-03-31 | Approved / IFI | FALSE | Complete
MDR-0512 | PRJ-028 | Pipeline Route Survey - OML 10 | Pipeline | R. Balogun | 1 | 2026-06-14 | 2026-07-02 | Approved / IFI | FALSE | Complete
MDR-0513 | PRJ-028 | HAZOP Report | Process | N. Effiong | 4 | 2026-04-25 | 2026-06-01 | Approved / IFI | FALSE | Complete
MDR-0514 | PRJ-028 | Piping GA Drawing - OML 10 | Piping | E. Danjuma | 1 | 2026-02-06 | 2026-03-01 | Approved / IFI | FALSE | Complete
MDR-0515 | PRJ-028 | Loop Diagram | Instrumentation | I. Briggs | 0 | 2026-01-23 | 2026-02-07 | Approved / IFI | FALSE | Complete
MDR-0516 | PRJ-028 | Structural Calculation Note | Civil / Structural | T. Ogundele | 0 | 2026-03-25 | 2026-04-10 | Approved / IFI | FALSE | Complete
MDR-0517 | PRJ-028 | Cable Schedule | Electrical | F. Etim | 2 | 2026-02-25 | 2026-03-27 | Approved / IFI | FALSE | Complete
MDR-0518 | PRJ-028 | Line List - OML 10 | Piping | U. Chukwuemeka | 4 | 2026-06-13 | 2026-07-02 | Approved / IFI | FALSE | Complete
MDR-0519 | PRJ-028 | Piping GA Drawing | Piping | I. Ogundele | 4 | 2026-03-01 | 2026-04-09 | Approved / IFI | FALSE | Complete
MDR-0520 | PRJ-028 | Line List | Piping | E. Danjuma | 0 | 2026-03-06 | 2026-03-20 | Approved / IFI | FALSE | Complete
MDR-0521 | PRJ-028 | Mechanical Handling Study - OML 10 | Mechanical | Q. Chukwu | 0 | 2026-02-04 | 2026-03-08 | Approved / IFI | FALSE | Complete
MDR-0522 | PRJ-028 | Piping Stress Report | Mechanical | Q. Chukwu | 4 | 2026-05-06 | 2026-05-29 | Approved / IFI | FALSE | Complete
MDR-0523 | PRJ-028 | Single Line Diagram | Electrical | C. James | 2 | 2026-05-04 | 2026-06-05 | Approved / IFI | FALSE | Complete
MDR-0524 | PRJ-028 | Steelwork Fabrication Drawing - OML 10 | Civil / Structural | M. Yakubu | 0 | 2026-02-24 | 2026-03-24 | Approved / IFI | FALSE | Complete
MDR-0525 | PRJ-028 | HAZOP Report - OML 10 | Process | S. Aliyu | 4 | 2026-07-14 | 2026-07-26 | Approved / IFI | FALSE | Complete
MDR-0526 | PRJ-028 | Piping Isometric | Piping | I. Ogundele | 4 | 2026-01-17 | 2026-01-29 | Approved / IFI | FALSE | Complete
MDR-0527 | GLB-001 | Single Line Diagram | Electrical | R. Ogunleye | 0 | 2026-06-07 | 2026-07-06 | Approved / IFI | FALSE | Complete
MDR-0528 | GLB-001 | Pipe Support Register - Global | Piping | I. Ogundele | 1 | 2026-04-30 | 2026-05-17 | Approved / IFI | FALSE | Complete
MDR-0529 | GLB-001 | Heat & Material Balance | Process | J. Musa | 1 | 2026-01-20 | 2026-02-22 | Approved / IFI | FALSE | Complete
MDR-0530 | GLB-001 | Process Flow Diagram - Global | Process | N. Effiong | 2 | 2026-01-28 | 2026-03-01 | Approved / IFI | FALSE | Complete
MDR-0531 | GLB-001 | Structural Calculation Note | Civil / Structural | M. Yakubu | 2 | 2026-04-23 | 2026-05-25 | Approved / IFI | FALSE | Complete
MDR-0532 | GLB-001 | Process Flow Diagram - Global | Process | J. Ibrahim | 3 | 2026-05-09 | 2026-06-09 | Approved / IFI | FALSE | Complete
MDR-0533 | GLB-001 | Control Narrative | Instrumentation | H. Sanni | 3 | 2026-05-16 | 2026-06-11 | Approved / IFI | FALSE | Complete
MDR-0534 | GLB-001 | Process Datasheet | Process | J. Ibrahim | 2 | 2026-05-24 | 2026-06-24 | Approved / IFI | FALSE | Complete
MDR-0535 | GLB-001 | Mechanical Handling Study - Global | Mechanical | D. Umeh | 1 | 2026-06-20 | 2026-07-21 | Approved / IFI | FALSE | Complete
MDR-0536 | GLB-001 | Piping Isometric - Global | Piping | E. Okoro | 0 | 2026-01-11 | 2026-02-10 | Approved / IFI | FALSE | Complete
MDR-0537 | GLB-001 | Control Narrative | Instrumentation | S. Aliyu | 1 | 2026-03-13 | 2026-04-12 | Approved / IFI | FALSE | Complete
MDR-0538 | GLB-001 | Lifting Plan - Global | Mechanical | D. Umeh | 1 | 2026-06-26 | 2026-08-01 | Approved / IFI | FALSE | Complete
MDR-0539 | GLB-001 | Piping Isometric | Piping | E. Okoro | 4 | 2026-04-01 | 2026-04-27 | Approved / IFI | FALSE | Complete
MDR-0540 | GLB-001 | Process Simulation Report - Global | Process | J. Musa | 4 | 2026-01-21 | 2026-02-03 | Approved / IFI | FALSE | Complete
MDR-0541 | GLB-001 | Process Flow Diagram | Process | N. Effiong | 4 | 2026-01-09 | 2026-02-07 | Approved / IFI | FALSE | Complete
MDR-0542 | GLB-001 | Pipe Support Register - Global | Piping | I. Ogundele | 3 | 2026-03-15 | 2026-04-11 | Approved / IFI | FALSE | Complete
MDR-0543 | GLB-001 | Pipe Support Register | Piping | E. Danjuma | 0 | 2026-04-26 | 2026-05-23 | Approved / IFI | FALSE | Complete
MDR-0544 | GLB-002 | Motor Datasheet | Electrical | C. James | 3 | 2026-05-06 | 2026-05-27 | Approved / IFI | FALSE | Complete
MDR-0545 | GLB-002 | Cable Schedule | Electrical | C. James | 2 | 2026-06-01 | 2026-06-18 | Approved / IFI | FALSE | Complete
MDR-0546 | GLB-002 | Process Datasheet | Process | J. Ibrahim | 4 | 2026-01-01 | 2026-02-04 | Approved / IFI | FALSE | Complete
MDR-0547 | GLB-002 | Loop Diagram - Global | Instrumentation | I. Briggs | 0 | 2026-04-08 | 2026-05-16 | Approved / IFI | FALSE | Complete
MDR-0548 | GLB-002 | Single Line Diagram | Electrical | M. Ekong | 3 | 2026-04-23 | 2026-05-06 | Approved / IFI | FALSE | Complete
MDR-0549 | GLB-002 | Foundation Design Report - Global | Civil / Structural | T. Ogundele | 3 | 2026-07-29 | 2026-08-10 | Approved / IFI | FALSE | Complete
MDR-0550 | GLB-002 | Control Narrative | Instrumentation | S. Aliyu | 0 | 2026-06-13 | 2026-06-25 | Approved / IFI | FALSE | Complete
MDR-0551 | GLB-002 | HAZOP Report | Process | N. Effiong | 0 | 2026-05-12 | 2026-06-11 | Approved / IFI | FALSE | Complete
MDR-0552 | GLB-002 | HAZOP Report - Global | Process | J. Ibrahim | 4 | 2026-01-15 | 2026-02-01 | Approved / IFI | FALSE | Complete
MDR-0553 | GLB-002 | Instrument Index | Instrumentation | S. Aliyu | 2 | 2026-04-19 | 2026-05-13 | Approved / IFI | FALSE | Complete
MDR-0554 | GLB-002 | HAZOP Report | Process | A. Musa | 2 | 2026-02-18 | 2026-03-25 | Approved / IFI | FALSE | Complete
MDR-0555 | GLB-002 | Material Take-Off | Piping | E. Okoro | 3 | 2026-04-10 | 2026-05-13 | Approved / IFI | FALSE | Complete
MDR-0556 | GLB-002 | Material Take-Off | Piping | E. Danjuma | 0 | 2026-04-28 | 2026-05-26 | Approved / IFI | FALSE | Complete
MDR-0557 | GLB-002 | P&ID | Process | S. Aliyu | 2 | 2026-05-22 | 2026-06-11 | Approved / IFI | FALSE | Complete
MDR-0558 | GLB-002 | Material Take-Off | Piping | I. Ogundele | 0 | 2026-06-24 | 2026-07-20 | Approved / IFI | FALSE | Complete
MDR-0559 | GLB-002 | Motor Datasheet | Electrical | R. Ogunleye | 2 | 2026-02-22 | 2026-03-27 | Approved / IFI | FALSE | Complete
MDR-0560 | GLB-002 | Pump Datasheet | Mechanical | B. Yusuf | 3 | 2026-06-30 | 2026-07-23 | Approved / IFI | FALSE | Complete
MDR-0561 | GLB-002 | Line List | Piping | P. Ndukwe | 1 | 2026-06-24 | 2026-07-19 | Approved / IFI | FALSE | Complete
MDR-0562 | GLB-002 | Line List | Piping | P. Ndukwe | 3 | 2026-07-31 | 2026-08-22 | Internal Development | FALSE | In Progress

## Risks
RiskID | ProjectID | RiskDescription | Category | Likelihood | Impact | Score | RiskLevel | Owner | MitigationAction | Status | RaisedDate | TargetCloseDate
RSK-001 | PRJ-024 | Electrical engineering capacity constrained against concurrent project demand | Schedule | 4 | 4 | 16 | High | Eng. Manager | Rebalance workload | Open | 2026-07-28 | 2026-09-05
RSK-002 | PRJ-024 | Long-lead compressor vendor data delayed against design programme | Schedule / Cost | 5 | 3 | 15 | High | Mechanical Lead | Expedite vendor | Open | 2026-07-21 | 2026-09-25
RSK-003 | PRJ-021 | Brownfield access window constrained by production shutdown schedule | Execution | 4 | 3 | 12 | Medium | Execution Lead | Confirm shutdown plan | Open | 2026-08-03 | 2026-10-25
RSK-004 | PRJ-022 | Contractor productivity below plan | Schedule | 4 | 2 | 8 | Medium | Execution Lead | Under review by project team | Open | 2026-07-15 | 2026-08-12
RSK-005 | PRJ-024 | Site access / permitting delay risk | Commercial | 5 | 5 | 25 | High | Discipline Lead | Under review by project team | Open | 2026-08-10 | 2026-09-23
RSK-006 | PRJ-020 | Third-party interface dependency | Commercial | 2 | 3 | 6 | Low | Project Manager | Under review by project team | Open | 2026-07-08 | 2026-09-29
RSK-007 | PRJ-024 | Design change from HAZOP / HAZID action | Execution | 3 | 3 | 9 | Medium | Discipline Lead | Under review by project team | Open | 2026-07-16 | 2026-08-24
RSK-008 | PRJ-008 | Interface misalignment between engineering and construction | Cost | 5 | 3 | 15 | High | Project Manager | Under review by project team | Open | 2026-08-03 | 2026-09-05
RSK-009 | PRJ-003 | Budget contingency erosion risk | Technical | 2 | 3 | 6 | Low | Project Manager | Under review by project team | Open | 2026-07-06 | 2026-09-22
RSK-010 | GLB-005 | Key resource attrition risk on critical path discipline | Technical | 3 | 3 | 9 | Medium | Eng. Manager | Under review by project team | Open | 2026-07-29 | 2026-09-18
RSK-011 | PRJ-023 | Regulatory approval timeline uncertainty | Safety | 4 | 4 | 16 | High | Execution Lead | Under review by project team | Open | 2026-06-24 | 2026-08-22
RSK-012 | PRJ-016 | Site access / permitting delay risk | Cost | 5 | 5 | 25 | High | Execution Lead | Under review by project team | Open | 2026-08-02 | 2026-09-22
RSK-013 | PRJ-023 | Scope growth not yet reflected in baseline | Cost | 3 | 2 | 6 | Low | Discipline Lead | Under review by project team | Open | 2026-06-19 | 2026-09-14
RSK-014 | PRJ-005 | Long-lead equipment delivery risk | Schedule | 5 | 3 | 15 | High | Project Manager | Under review by project team | Open | 2026-06-20 | 2026-08-31
RSK-015 | PRJ-018 | Budget contingency erosion risk | Execution | 3 | 3 | 9 | Medium | Project Controls Lead | Under review by project team | Open | 2026-08-01 | 2026-10-14
RSK-016 | PRJ-023 | Contractor productivity below plan | Technical | 3 | 2 | 6 | Low | Project Controls Lead | Under review by project team | Open | 2026-07-02 | 2026-09-05
RSK-017 | GLB-005 | Budget contingency erosion risk | Safety | 2 | 2 | 4 | Low | Project Controls Lead | Under review by project team | Open | 2026-07-20 | 2026-08-26
RSK-018 | GLB-005 | Vendor data quality below required standard | Execution | 3 | 2 | 6 | Low | Project Controls Lead | Under review by project team | Open | 2026-06-29 | 2026-07-26
RSK-019 | PRJ-010 | Weather / seasonal access constraint | Safety | 2 | 3 | 6 | Low | Discipline Lead | Under review by project team | Open | 2026-06-26 | 2026-07-21
RSK-020 | PRJ-015 | Long-lead equipment delivery risk | Commercial | 3 | 3 | 9 | Medium | Execution Lead | Under review by project team | Open | 2026-06-20 | 2026-08-07
RSK-021 | PRJ-020 | Long-lead equipment delivery risk | Technical | 3 | 3 | 9 | Medium | Execution Lead | Under review by project team | Open | 2026-07-19 | 2026-10-14
RSK-022 | PRJ-012 | Regulatory approval timeline uncertainty | Schedule | 2 | 5 | 10 | Medium | Eng. Manager | Under review by project team | Open | 2026-07-05 | 2026-07-29
RSK-023 | PRJ-020 | Long-lead equipment delivery risk | Safety | 2 | 2 | 4 | Low | Project Controls Lead | Under review by project team | Open | 2026-08-01 | 2026-09-19
RSK-024 | PRJ-018 | Budget contingency erosion risk | Safety | 3 | 4 | 12 | Medium | Project Manager | Under review by project team | Open | 2026-07-21 | 2026-10-08
RSK-025 | PRJ-004 | Contractor productivity below plan | Commercial | 5 | 2 | 10 | Medium | Project Manager | Under review by project team | Open | 2026-06-21 | 2026-07-16
RSK-026 | PRJ-019 | Third-party interface dependency | Safety | 2 | 3 | 6 | Low | Discipline Lead | Under review by project team | Open | 2026-06-28 | 2026-09-04
RSK-027 | PRJ-023 | Design change from HAZOP / HAZID action | Cost | 3 | 2 | 6 | Low | Execution Lead | Under review by project team | Open | 2026-06-21 | 2026-09-04
RSK-028 | PRJ-003 | Interface misalignment between engineering and construction | Schedule | 2 | 5 | 10 | Medium | Discipline Lead | Under review by project team | Open | 2026-08-14 | 2026-10-17
RSK-029 | GLB-003 | Contractor productivity below plan | Safety | 3 | 2 | 6 | Low | Eng. Manager | Mitigated and closed out | Closed | 2026-06-06 | 2026-08-08
RSK-030 | PRJ-024 | Interface misalignment between engineering and construction | Cost | 3 | 1 | 3 | Low | Discipline Lead | Mitigated and closed out | Closed | 2026-04-01 | 2026-05-25
RSK-031 | PRJ-007 | Interface misalignment between engineering and construction | Schedule | 1 | 3 | 3 | Low | Eng. Manager | Mitigated and closed out | Closed | 2026-06-13 | 2026-07-03
RSK-032 | GLB-003 | Regulatory approval timeline uncertainty | Cost | 2 | 3 | 6 | Low | Eng. Manager | Mitigated and closed out | Closed | 2026-02-21 | 2026-04-01
RSK-033 | GLB-005 | Regulatory approval timeline uncertainty | Safety | 2 | 3 | 6 | Low | Project Manager | Mitigated and closed out | Closed | 2026-05-03 | 2026-07-23
RSK-034 | PRJ-026 | Third-party interface dependency | Schedule | 2 | 3 | 6 | Low | Eng. Manager | Mitigated and closed out | Closed | 2026-01-29 | 2026-04-07

## Issues
IssueID | ProjectID | IssueDescription | Severity | Owner | RaisedDate | Status | TargetCloseDate
ISS-001 | PRJ-018 | Field query awaiting engineering response | Medium | Discipline Lead | 2026-07-24 | Open | 2026-08-18
ISS-002 | PRJ-012 | Non-conformance report open against fabrication | Medium | Eng. Manager | 2026-07-15 | Open | 2026-08-09
ISS-003 | PRJ-018 | As-built discrepancy against design drawing | Low | Eng. Manager | 2026-06-23 | Open | 2026-07-29
ISS-004 | PRJ-003 | Vendor document non-conformance | Medium | Discipline Lead | 2026-07-30 | Open | 2026-08-15
ISS-005 | PRJ-022 | Design clash identified during 3D model review | Low | Eng. Manager | 2026-07-24 | Open | 2026-08-15
ISS-006 | PRJ-001 | Missing interface data from adjacent project | Medium | Project Manager | 2026-06-19 | Open | 2026-08-01
ISS-007 | PRJ-004 | Vendor document non-conformance | Low | Discipline Lead | 2026-07-24 | Open | 2026-08-13
ISS-008 | PRJ-021 | Field query awaiting engineering response | Low | Discipline Lead | 2026-07-21 | Open | 2026-08-10
ISS-009 | PRJ-003 | As-built discrepancy against design drawing | High | Eng. Manager | 2026-08-13 | Open | 2026-09-04
ISS-010 | GLB-005 | Vendor document non-conformance | Medium | Eng. Manager | 2026-07-27 | Open | 2026-08-19
ISS-011 | GLB-004 | Missing interface data from adjacent project | Medium | Discipline Lead | 2026-07-27 | Open | 2026-09-09
ISS-012 | PRJ-020 | Non-conformance report open against fabrication | Low | Eng. Manager | 2026-07-07 | Open | 2026-07-30
ISS-013 | PRJ-012 | As-built discrepancy against design drawing | High | Eng. Manager | 2026-06-29 | Open | 2026-08-08
ISS-014 | PRJ-015 | Non-conformance report open against fabrication | Medium | Project Manager | 2026-08-11 | Open | 2026-08-28
ISS-015 | PRJ-003 | Missing interface data from adjacent project | Low | Eng. Manager | 2026-07-12 | Open | 2026-08-24
ISS-016 | PRJ-018 | Missing interface data from adjacent project | Medium | Eng. Manager | 2026-06-27 | Open | 2026-07-07

## Actions
ActionID | ProjectID | ActionDescription | Owner | DueDate | Status | IsOverdue
ACT-001 | PRJ-014 | Confirm shutdown access dates with Operations | Project Manager | 2026-08-28 | Open | FALSE
ACT-002 | PRJ-026 | Finalise resource rebalancing plan | Discipline Lead | 2026-09-03 | Open | FALSE
ACT-003 | PRJ-010 | Close out HAZOP action item | Project Manager | 2026-08-06 | Open | TRUE
ACT-004 | PRJ-003 | Submit revised vendor data request | Project Controls Lead | 2026-08-13 | Open | TRUE
ACT-005 | PRJ-021 | Confirm shutdown access dates with Operations | Eng. Manager | 2026-08-06 | Open | TRUE
ACT-006 | PRJ-015 | Finalise resource rebalancing plan | Project Manager | 2026-09-11 | Open | FALSE
ACT-007 | PRJ-011 | Confirm shutdown access dates with Operations | Eng. Manager | 2026-08-31 | Open | FALSE
ACT-008 | PRJ-022 | Submit revised vendor data request | Eng. Manager | 2026-08-09 | Open | TRUE
ACT-009 | PRJ-005 | Close out HAZOP action item | Discipline Lead | 2026-09-05 | Open | FALSE
ACT-010 | PRJ-004 | Close out HAZOP action item | Project Manager | 2026-09-11 | Open | FALSE
ACT-011 | PRJ-014 | Confirm shutdown access dates with Operations | Project Controls Lead | 2026-08-29 | Open | FALSE
ACT-012 | PRJ-007 | Confirm shutdown access dates with Operations | Project Controls Lead | 2026-09-02 | Open | FALSE
ACT-013 | PRJ-004 | Issue revised P&ID for review | Project Manager | 2026-08-22 | Open | FALSE
ACT-014 | PRJ-005 | Update project schedule baseline | Project Manager | 2026-08-16 | Open | FALSE
ACT-015 | PRJ-020 | Issue revised P&ID for review | Project Manager | 2026-09-07 | Open | FALSE
ACT-016 | GLB-004 | Confirm shutdown access dates with Operations | Eng. Manager | 2026-08-17 | Open | FALSE
ACT-017 | PRJ-019 | Submit revised vendor data request | Project Controls Lead | 2026-08-23 | Open | FALSE
ACT-018 | PRJ-011 | Close out HAZOP action item | Eng. Manager | 2026-09-09 | Open | FALSE
ACT-019 | PRJ-026 | Complete interface data exchange | Eng. Manager | 2026-09-13 | Open | FALSE

## ChangeRequests
ChangeRequestID | ProjectID | Description | Status | RaisedDate | Impact
CR-001 | PRJ-013 | Extended metering skid scope to include prover loop | Approved | 2026-07-28 | Scope
CR-002 | PRJ-020 | Scope reduction following optioneering study | Under Review | 2026-07-07 | Schedule
CR-003 | PRJ-011 | Additional well slot scope addition | Approved | 2026-07-25 | Cost
CR-004 | PRJ-024 | Schedule extension request due to vendor delay | Pending Approval | 2026-07-15 | Scope
CR-005 | PRJ-019 | Budget increase request for long-lead items | Under Review | 2026-07-28 | Schedule
CR-006 | PRJ-016 | Extended metering skid scope to include prover loop | Under Review | 2026-07-15 | Cost

## Milestones
MilestoneID | ProjectID | MilestoneName | MilestoneType | TargetDate | Status | ActualDate
MS-001 | PRJ-024 | Basis of Design | Milestone | 2026-07-22 | Done | 2026-07-22
MS-002 | PRJ-024 | HAZID Workshop | Milestone | 2026-07-31 | Done | 2026-07-31
MS-003 | PRJ-024 | HAZOP Closeout | Milestone | 2026-08-17 | Next
MS-004 | PRJ-024 | Define Gate Readiness | Gate | 2026-08-22 | At Risk
MS-005 | PRJ-024 | Mechanical Design Complete | Milestone | 2026-08-25 | In Progress
MS-006 | PRJ-024 | Define Gate Approval | Gate | 2026-08-29 | Upcoming
MS-007 | PRJ-021 | Implementation Start | Milestone | 2026-09-04 | On Track
MS-008 | PRJ-021 | Shutdown Window Confirmed | Milestone | 2026-08-20 | Done | 2026-08-18
MS-009 | PRJ-021 | Execute Gate Approval | Gate | 2026-11-10 | On Track
MS-010 | PRJ-018 | Concept Options Workshop | Milestone | 2026-09-26 | Upcoming
MS-011 | PRJ-018 | Assess Gate Review | Gate | 2027-01-02 | Upcoming
MS-012 | PRJ-015 | Basis of Design | Milestone | 2025-12-12 | Done | 2025-12-11
MS-013 | PRJ-015 | HAZID Workshop | Milestone | 2026-03-10 | Done | 2026-03-12
MS-014 | PRJ-015 | HAZOP Closeout | Milestone | 2026-06-05 | Done | 2026-06-07
MS-015 | PRJ-015 | Define Gate Approval | Gate | 2026-09-01 | Upcoming
MS-016 | PRJ-011 | Detailed Design Complete | Milestone | 2025-09-28 | Done | 2025-09-29
MS-017 | PRJ-011 | Procurement Complete | Milestone | 2026-01-07 | Done | 2026-01-11
MS-018 | PRJ-011 | Construction Complete | Milestone | 2026-04-19 | Done | 2026-04-22
MS-019 | PRJ-011 | Execute Gate Approval | Gate | 2026-07-29 | Done | 2026-07-31
MS-020 | GLB-003 | Concept Options Workshop | Milestone | 2026-09-18 | Upcoming
MS-021 | GLB-003 | Assess Gate Review | Gate | 2027-01-05 | Upcoming
MS-022 | PRJ-006 | MDR Closeout | Milestone | 2025-06-26 | Done | 2025-06-29
MS-023 | PRJ-006 | Lessons Learned Workshop | Milestone | 2025-11-21 | Done | 2025-11-21
MS-024 | PRJ-006 | Archive Sign-off | Milestone | 2026-04-17 | Done | 2026-04-14
MS-025 | PRJ-009 | MDR Closeout | Milestone | 2025-03-12 | Done | 2025-03-10
MS-026 | PRJ-009 | Lessons Learned Workshop | Milestone | 2025-09-02 | Done | 2025-08-30
MS-027 | PRJ-009 | Archive Sign-off | Milestone | 2026-02-22 | Done | 2026-02-22
MS-028 | PRJ-005 | Concept Options Workshop | Milestone | 2026-07-29 | Done | 2026-07-29
MS-029 | PRJ-005 | Assess Gate Review | Gate | 2026-11-16 | Upcoming
MS-030 | PRJ-008 | Concept Options Workshop | Milestone | 2026-08-23 | In Progress
MS-031 | PRJ-008 | Assess Gate Review | Gate | 2026-12-12 | Upcoming
MS-032 | PRJ-013 | Select Gate Review | Gate | 2026-07-27 | Done | 2026-07-26
MS-033 | PRJ-013 | Preferred Concept Sign-off | Milestone | 2026-11-01 | Upcoming
MS-034 | PRJ-019 | Identify Gate Review | Gate | 2027-02-20 | Upcoming
MS-035 | PRJ-023 | Concept Options Workshop | Milestone | 2026-09-19 | Upcoming
MS-036 | PRJ-023 | Assess Gate Review | Gate | 2026-12-13 | Upcoming
MS-037 | GLB-004 | Select Gate Review | Gate | 2026-06-28 | Done | 2026-06-30
MS-038 | GLB-004 | Preferred Concept Sign-off | Milestone | 2026-10-16 | Upcoming
MS-039 | PRJ-001 | Basis of Design | Milestone | 2026-04-22 | Done | 2026-04-23
MS-040 | PRJ-001 | HAZID Workshop | Milestone | 2026-06-21 | Done | 2026-06-24
MS-041 | PRJ-001 | HAZOP Closeout | Milestone | 2026-08-21 | In Progress
MS-042 | PRJ-001 | Define Gate Approval | Gate | 2026-10-21 | Upcoming
MS-043 | PRJ-003 | Basis of Design | Milestone | 2026-01-19 | Done | 2026-01-19
MS-044 | PRJ-003 | HAZID Workshop | Milestone | 2026-04-10 | Done | 2026-04-11
MS-045 | PRJ-003 | HAZOP Closeout | Milestone | 2026-06-30 | Done | 2026-07-05
MS-046 | PRJ-003 | Define Gate Approval | Gate | 2026-09-19 | Upcoming
MS-047 | PRJ-007 | Basis of Design | Milestone | 2026-02-01 | Done | 2026-02-02
MS-048 | PRJ-007 | HAZID Workshop | Milestone | 2026-04-30 | Done | 2026-04-29
MS-049 | PRJ-007 | HAZOP Closeout | Milestone | 2026-07-26 | Done | 2026-07-24
MS-050 | PRJ-007 | Define Gate Approval | Gate | 2026-10-22 | Upcoming
MS-051 | PRJ-010 | Basis of Design | Milestone | 2026-04-06 | Done | 2026-04-08
MS-052 | PRJ-010 | HAZID Workshop | Milestone | 2026-06-26 | Done | 2026-06-30
MS-053 | PRJ-010 | HAZOP Closeout | Milestone | 2026-09-15 | Upcoming
MS-054 | PRJ-010 | Define Gate Approval | Gate | 2026-12-05 | Upcoming
MS-055 | PRJ-014 | Basis of Design | Milestone | 2025-12-05 | Done | 2025-12-06
MS-056 | PRJ-014 | HAZID Workshop | Milestone | 2026-03-03 | Done | 2026-03-04
MS-057 | PRJ-014 | HAZOP Closeout | Milestone | 2026-05-29 | Done | 2026-05-26
MS-058 | PRJ-014 | Define Gate Approval | Gate | 2026-08-25 | In Progress
MS-059 | PRJ-020 | Basis of Design | Milestone | 2026-05-04 | Done | 2026-05-03
MS-060 | PRJ-020 | HAZID Workshop | Milestone | 2026-07-24 | Done | 2026-07-28
MS-061 | PRJ-020 | HAZOP Closeout | Milestone | 2026-10-13 | Upcoming
MS-062 | PRJ-020 | Define Gate Approval | Gate | 2027-01-02 | Upcoming
MS-063 | GLB-005 | Basis of Design | Milestone | 2026-04-20 | Done | 2026-04-19
MS-064 | GLB-005 | HAZID Workshop | Milestone | 2026-07-03 | Done | 2026-07-01
MS-065 | GLB-005 | HAZOP Closeout | Milestone | 2026-09-16 | Upcoming
MS-066 | GLB-005 | Define Gate Approval | Gate | 2026-11-29 | Upcoming
MS-067 | PRJ-004 | Detailed Design Complete | Milestone | 2025-08-18 | Done | 2025-08-16
MS-068 | PRJ-004 | Procurement Complete | Milestone | 2025-12-11 | Done | 2025-12-15
MS-069 | PRJ-004 | Construction Complete | Milestone | 2026-04-05 | Done | 2026-04-05
MS-070 | PRJ-004 | Execute Gate Approval | Gate | 2026-07-29 | Done | 2026-07-29
MS-071 | PRJ-012 | Detailed Design Complete | Milestone | 2025-06-13 | Done | 2025-06-14
MS-072 | PRJ-012 | Procurement Complete | Milestone | 2025-10-19 | Done | 2025-10-18
MS-073 | PRJ-012 | Construction Complete | Milestone | 2026-02-25 | Done | 2026-02-24
MS-074 | PRJ-012 | Execute Gate Approval | Gate | 2026-07-03 | Done | 2026-07-04
MS-075 | PRJ-016 | Detailed Design Complete | Milestone | 2026-01-01 | Done | 2025-12-29
MS-076 | PRJ-016 | Procurement Complete | Milestone | 2026-04-05 | Done | 2026-04-08
MS-077 | PRJ-016 | Construction Complete | Milestone | 2026-07-09 | Done | 2026-07-13
MS-078 | PRJ-016 | Execute Gate Approval | Gate | 2026-10-12 | Upcoming
MS-079 | PRJ-022 | Detailed Design Complete | Milestone | 2025-10-06 | Done | 2025-10-05
MS-080 | PRJ-022 | Procurement Complete | Milestone | 2026-01-22 | Done | 2026-01-20
MS-081 | PRJ-022 | Construction Complete | Milestone | 2026-05-11 | Done | 2026-05-11
MS-082 | PRJ-022 | Execute Gate Approval | Gate | 2026-08-27 | Upcoming
MS-083 | PRJ-026 | Detailed Design Complete | Milestone | 2025-09-15 | Done | 2025-09-14
MS-084 | PRJ-026 | Procurement Complete | Milestone | 2026-01-02 | Done | 2025-12-30
MS-085 | PRJ-026 | Construction Complete | Milestone | 2026-04-20 | Done | 2026-04-19
MS-086 | PRJ-026 | Execute Gate Approval | Gate | 2026-08-07 | Done | 2026-08-10
MS-087 | PRJ-017 | MDR Closeout | Milestone | 2025-05-29 | Done | 2025-06-02
MS-088 | PRJ-017 | Lessons Learned Workshop | Milestone | 2025-11-10 | Done | 2025-11-12
MS-089 | PRJ-017 | Archive Sign-off | Milestone | 2026-04-24 | Done | 2026-04-21
MS-090 | PRJ-027 | MDR Closeout | Milestone | 2025-05-15 | Done | 2025-05-19
MS-091 | PRJ-027 | Lessons Learned Workshop | Milestone | 2025-10-19 | Done | 2025-10-20
MS-092 | PRJ-027 | Archive Sign-off | Milestone | 2026-03-24 | Done | 2026-03-29
MS-093 | PRJ-028 | MDR Closeout | Milestone | 2025-03-20 | Done | 2025-03-20
MS-094 | PRJ-028 | Lessons Learned Workshop | Milestone | 2025-09-10 | Done | 2025-09-14
MS-095 | PRJ-028 | Archive Sign-off | Milestone | 2026-03-02 | Done | 2026-03-04
MS-096 | GLB-001 | MDR Closeout | Milestone | 2025-06-30 | Done | 2025-07-01
MS-097 | GLB-001 | Lessons Learned Workshop | Milestone | 2025-10-29 | Done | 2025-10-29
MS-098 | GLB-001 | Archive Sign-off | Milestone | 2026-02-28 | Done | 2026-03-05
MS-099 | GLB-002 | MDR Closeout | Milestone | 2025-04-08 | Done | 2025-04-10
MS-100 | GLB-002 | Lessons Learned Workshop | Milestone | 2025-08-24 | Done | 2025-08-27
MS-101 | GLB-002 | Archive Sign-off | Milestone | 2026-01-10 | Done | 2026-01-14

## Schedule_Activities
ActivityID | ProjectID | ActivityName | StartDate | EndDate | PctComplete
GNT-001 | PRJ-024 | Process Design | 2025-11-22 | 2026-03-04 | 100
GNT-002 | PRJ-024 | Mechanical Design | 2026-01-03 | 2026-05-26 | 75
GNT-003 | PRJ-024 | Piping Design | 2026-02-13 | 2026-07-22 | 86
GNT-004 | PRJ-024 | E&I Design | 2026-03-07 | 2026-08-04 | 80
GNT-005 | PRJ-024 | Define Gate | 2026-04-30 | 2026-08-29 | 52
GNT-006 | PRJ-021 | Detailed Design | 2025-05-10 | 2025-11-18 | 76
GNT-007 | PRJ-021 | Procurement | 2025-07-31 | 2026-04-04 | 65
GNT-008 | PRJ-021 | Construction | 2025-11-18 | 2026-09-16 | 69
GNT-009 | PRJ-021 | Commissioning | 2026-07-23 | 2026-10-30 | 18
GNT-010 | PRJ-021 | Execute Gate | 2026-10-14 | 2026-11-10 | 39
GNT-011 | PRJ-018 | Concept Study | 2026-06-20 | 2026-11-02 | 61
GNT-012 | PRJ-018 | Options Assessment | 2026-09-14 | 2027-01-02 | 73
GNT-013 | PRJ-018 | Assess Gate | 2026-12-21 | 2027-02-20 | 2
GNT-014 | PRJ-015 | Process Design | 2025-10-17 | 2026-03-12 | 84
GNT-015 | PRJ-015 | Mechanical Design | 2025-12-03 | 2026-06-11 | 76
GNT-016 | PRJ-015 | Piping Design | 2026-01-11 | 2026-08-17 | 89
GNT-017 | PRJ-015 | E&I Design | 2026-02-20 | 2026-09-06 | 41
GNT-018 | PRJ-015 | Define Gate | 2026-05-10 | 2026-10-15 | 28
GNT-019 | PRJ-011 | Detailed Design | 2025-06-18 | 2025-11-25 | 97
GNT-020 | PRJ-011 | Procurement | 2025-08-26 | 2026-03-19 | 67
GNT-021 | PRJ-011 | Construction | 2025-11-25 | 2026-08-03 | 84
GNT-022 | PRJ-011 | Commissioning | 2026-06-19 | 2026-09-09 | 25
GNT-023 | PRJ-011 | Execute Gate | 2026-08-26 | 2026-09-18 | 39
GNT-024 | GLB-003 | Concept Study | 2026-06-01 | 2026-10-29 | 65
GNT-025 | GLB-003 | Options Assessment | 2026-09-05 | 2027-01-05 | 42
GNT-026 | GLB-003 | Assess Gate | 2026-12-23 | 2027-03-01 | 36
GNT-027 | PRJ-005 | Concept Study | 2026-04-10 | 2026-09-08 | 70
GNT-028 | PRJ-005 | Options Assessment | 2026-07-15 | 2026-11-16 | 82
GNT-029 | PRJ-005 | Assess Gate | 2026-11-02 | 2027-01-10 | 22
GNT-030 | PRJ-008 | Concept Study | 2026-05-05 | 2026-10-04 | 89
GNT-031 | PRJ-008 | Options Assessment | 2026-08-10 | 2026-12-12 | 48
GNT-032 | PRJ-008 | Assess Gate | 2026-11-28 | 2027-02-05 | 10
GNT-033 | PRJ-013 | Concept Selection | 2026-04-20 | 2026-08-20 | 77
GNT-034 | PRJ-013 | Select Gate | 2026-10-08 | 2026-12-20 | 12
GNT-035 | PRJ-019 | Opportunity Framing | 2026-12-01 | 2027-02-12 | 47
GNT-036 | PRJ-019 | Identify Gate | 2027-02-06 | 2027-04-01 | 48
GNT-037 | PRJ-023 | Concept Study | 2026-06-25 | 2026-10-21 | 81
GNT-038 | PRJ-023 | Options Assessment | 2026-09-08 | 2026-12-13 | 53
GNT-039 | PRJ-023 | Assess Gate | 2026-12-02 | 2027-01-25 | 10
GNT-040 | GLB-004 | Concept Selection | 2026-03-10 | 2026-07-26 | 72
GNT-041 | GLB-004 | Select Gate | 2026-09-18 | 2026-12-10 | 27
GNT-042 | PRJ-001 | Process Design | 2026-03-14 | 2026-06-23 | 98
GNT-043 | PRJ-001 | Mechanical Design | 2026-04-16 | 2026-08-25 | 59
GNT-044 | PRJ-001 | Piping Design | 2026-05-13 | 2026-10-10 | 45
GNT-045 | PRJ-001 | E&I Design | 2026-06-09 | 2026-10-24 | 44
GNT-046 | PRJ-001 | Define Gate | 2026-08-03 | 2026-11-20 | 17
GNT-047 | PRJ-003 | Process Design | 2025-11-28 | 2026-04-12 | 93
GNT-048 | PRJ-003 | Mechanical Design | 2026-01-11 | 2026-07-05 | 51
GNT-049 | PRJ-003 | Piping Design | 2026-02-17 | 2026-09-05 | 61
GNT-050 | PRJ-003 | E&I Design | 2026-03-25 | 2026-09-23 | 41
GNT-051 | PRJ-003 | Define Gate | 2026-06-06 | 2026-10-30 | 25
GNT-052 | PRJ-007 | Process Design | 2025-12-07 | 2026-05-02 | 99
GNT-053 | PRJ-007 | Mechanical Design | 2026-01-23 | 2026-08-01 | 49
GNT-054 | PRJ-007 | Piping Design | 2026-03-03 | 2026-10-07 | 81
GNT-055 | PRJ-007 | E&I Design | 2026-04-12 | 2026-10-27 | 63
GNT-056 | PRJ-007 | Define Gate | 2026-06-30 | 2026-12-05 | 1
GNT-057 | PRJ-010 | Process Design | 2026-02-13 | 2026-06-28 | 84
GNT-058 | PRJ-010 | Mechanical Design | 2026-03-29 | 2026-09-20 | 85
GNT-059 | PRJ-010 | Piping Design | 2026-05-05 | 2026-11-21 | 69
GNT-060 | PRJ-010 | E&I Design | 2026-06-10 | 2026-12-09 | 69
GNT-061 | PRJ-010 | Define Gate | 2026-08-22 | 2027-01-15 | 23
GNT-062 | PRJ-014 | Process Design | 2025-10-10 | 2026-03-05 | 73
GNT-063 | PRJ-014 | Mechanical Design | 2025-11-26 | 2026-06-04 | 62
GNT-064 | PRJ-014 | Piping Design | 2026-01-04 | 2026-08-10 | 71
GNT-065 | PRJ-014 | E&I Design | 2026-02-13 | 2026-08-30 | 40
GNT-066 | PRJ-014 | Define Gate | 2026-05-03 | 2026-10-08 | 1
GNT-067 | PRJ-020 | Process Design | 2026-03-13 | 2026-07-26 | 95
GNT-068 | PRJ-020 | Mechanical Design | 2026-04-26 | 2026-10-18 | 89
GNT-069 | PRJ-020 | Piping Design | 2026-06-02 | 2026-12-19 | 55
GNT-070 | PRJ-020 | E&I Design | 2026-07-08 | 2027-01-06 | 76
GNT-071 | PRJ-020 | Define Gate | 2026-09-19 | 2027-02-12 | 8
GNT-072 | GLB-005 | Process Design | 2026-03-04 | 2026-07-05 | 70
GNT-073 | GLB-005 | Mechanical Design | 2026-04-13 | 2026-09-20 | 52
GNT-074 | GLB-005 | Piping Design | 2026-05-16 | 2026-11-16 | 75
GNT-075 | GLB-005 | E&I Design | 2026-06-19 | 2026-12-03 | 69
GNT-076 | GLB-005 | Define Gate | 2026-08-24 | 2027-01-05 | 31
GNT-077 | PRJ-004 | Detailed Design | 2025-04-25 | 2025-10-23 | 90
GNT-078 | PRJ-004 | Procurement | 2025-07-12 | 2026-03-02 | 53
GNT-079 | PRJ-004 | Construction | 2025-10-23 | 2026-08-04 | 45
GNT-080 | PRJ-004 | Commissioning | 2026-06-13 | 2026-09-15 | 2
GNT-081 | PRJ-004 | Execute Gate | 2026-08-30 | 2026-09-25 | 2
GNT-082 | PRJ-012 | Detailed Design | 2025-02-05 | 2025-08-26 | 90
GNT-083 | PRJ-012 | Procurement | 2025-05-03 | 2026-01-17 | 59
GNT-084 | PRJ-012 | Construction | 2025-08-26 | 2026-07-09 | 54
GNT-085 | PRJ-012 | Commissioning | 2026-05-13 | 2026-08-24 | 24
GNT-086 | PRJ-012 | Execute Gate | 2026-08-07 | 2026-09-05 | 26
GNT-087 | PRJ-016 | Detailed Design | 2025-09-28 | 2026-02-24 | 97
GNT-088 | PRJ-016 | Procurement | 2025-12-01 | 2026-06-11 | 87
GNT-089 | PRJ-016 | Construction | 2026-02-24 | 2026-10-16 | 44
GNT-090 | PRJ-016 | Commissioning | 2026-09-04 | 2026-11-19 | 9
GNT-091 | PRJ-016 | Execute Gate | 2026-11-07 | 2026-11-28 | 8
GNT-092 | PRJ-022 | Detailed Design | 2025-06-20 | 2025-12-07 | 97
GNT-093 | PRJ-022 | Procurement | 2025-09-01 | 2026-04-08 | 56
GNT-094 | PRJ-022 | Construction | 2025-12-07 | 2026-09-01 | 60
GNT-095 | PRJ-022 | Commissioning | 2026-07-15 | 2026-10-10 | 26
GNT-096 | PRJ-022 | Execute Gate | 2026-09-26 | 2026-10-20 | 18
GNT-097 | PRJ-026 | Detailed Design | 2025-05-30 | 2025-11-17 | 77
GNT-098 | PRJ-026 | Procurement | 2025-08-11 | 2026-03-19 | 59
GNT-099 | PRJ-026 | Construction | 2025-11-17 | 2026-08-12 | 74
GNT-100 | PRJ-026 | Commissioning | 2026-06-24 | 2026-09-20 | 10
GNT-101 | PRJ-026 | Execute Gate | 2026-09-06 | 2026-09-30 | 5

## SCurve_Monthly
ProjectID | MonthDate | PlannedPct | ActualPct
PRJ-024 | 2026-01-01 | 11 | 10
PRJ-024 | 2026-02-01 | 20 | 18
PRJ-024 | 2026-03-01 | 29 | 26
PRJ-024 | 2026-04-01 | 39 | 36
PRJ-024 | 2026-05-01 | 49 | 46
PRJ-024 | 2026-06-01 | 59 | 54
PRJ-024 | 2026-07-01 | 66 | 62
PRJ-024 | 2026-08-01 | 71 | 67
PRJ-024 | 2026-09-01 | 72
PRJ-024 | 2026-10-01 | 72
PRJ-024 | 2026-11-01 | 72
PRJ-024 | 2026-12-01 | 72
PRJ-021 | 2026-01-01 | 32 | 32
PRJ-021 | 2026-02-01 | 39 | 38
PRJ-021 | 2026-03-01 | 45 | 44
PRJ-021 | 2026-04-01 | 51 | 51
PRJ-021 | 2026-05-01 | 58 | 57
PRJ-021 | 2026-06-01 | 64 | 63
PRJ-021 | 2026-07-01 | 69 | 68
PRJ-021 | 2026-08-01 | 73 | 72
PRJ-021 | 2026-09-01 | 77
PRJ-021 | 2026-10-01 | 79
PRJ-021 | 2026-11-01 | 80
PRJ-021 | 2026-12-01 | 80
PRJ-018 | 2026-01-01 | 0 | 0
PRJ-018 | 2026-02-01 | 0 | 0
PRJ-018 | 2026-03-01 | 0 | 0
PRJ-018 | 2026-04-01 | 0 | 0
PRJ-018 | 2026-05-01 | 0 | 0
PRJ-018 | 2026-06-01 | 0 | 0
PRJ-018 | 2026-07-01 | 2 | 2
PRJ-018 | 2026-08-01 | 25 | 22
PRJ-018 | 2026-09-01 | 69
PRJ-018 | 2026-10-01 | 100
PRJ-018 | 2026-11-01 | 100
PRJ-018 | 2026-12-01 | 100
PRJ-015 | 2026-01-01 | 11 | 10
PRJ-015 | 2026-02-01 | 18 | 15
PRJ-015 | 2026-03-01 | 24 | 21
PRJ-015 | 2026-04-01 | 31 | 27
PRJ-015 | 2026-05-01 | 38 | 33
PRJ-015 | 2026-06-01 | 45 | 40
PRJ-015 | 2026-07-01 | 51 | 45
PRJ-015 | 2026-08-01 | 56 | 50
PRJ-015 | 2026-09-01 | 60
PRJ-015 | 2026-10-01 | 62
PRJ-015 | 2026-11-01 | 62
PRJ-015 | 2026-12-01 | 62
PRJ-011 | 2026-01-01 | 34 | 35
PRJ-011 | 2026-02-01 | 43 | 44
PRJ-011 | 2026-03-01 | 50 | 52
PRJ-011 | 2026-04-01 | 59 | 60
PRJ-011 | 2026-05-01 | 66 | 68
PRJ-011 | 2026-06-01 | 73 | 75
PRJ-011 | 2026-07-01 | 79 | 81
PRJ-011 | 2026-08-01 | 83 | 85
PRJ-011 | 2026-09-01 | 85
PRJ-011 | 2026-10-01 | 85
PRJ-011 | 2026-11-01 | 85
PRJ-011 | 2026-12-01 | 85
GLB-003 | 2026-01-01 | 0 | 0
GLB-003 | 2026-02-01 | 0 | 0
GLB-003 | 2026-03-01 | 0 | 0
GLB-003 | 2026-04-01 | 0 | 0
GLB-003 | 2026-05-01 | 0 | 0
GLB-003 | 2026-06-01 | 0 | 0
GLB-003 | 2026-07-01 | 8 | 8
GLB-003 | 2026-08-01 | 31 | 30
GLB-003 | 2026-09-01 | 64
GLB-003 | 2026-10-01 | 100
GLB-003 | 2026-11-01 | 100
GLB-003 | 2026-12-01 | 100
PRJ-005 | 2026-01-01 | 0 | 0
PRJ-005 | 2026-02-01 | 0 | 0
PRJ-005 | 2026-03-01 | 0 | 0
PRJ-005 | 2026-04-01 | 0 | 0
PRJ-005 | 2026-05-01 | 1 | 1
PRJ-005 | 2026-06-01 | 7 | 6
PRJ-005 | 2026-07-01 | 15 | 13
PRJ-005 | 2026-08-01 | 27 | 23
PRJ-005 | 2026-09-01 | 39
PRJ-005 | 2026-10-01 | 50
PRJ-005 | 2026-11-01 | 61
PRJ-005 | 2026-12-01 | 68
PRJ-008 | 2026-01-01 | 0 | 0
PRJ-008 | 2026-02-01 | 0 | 0
PRJ-008 | 2026-03-01 | 0 | 0
PRJ-008 | 2026-04-01 | 0 | 0
PRJ-008 | 2026-05-01 | 0 | 0
PRJ-008 | 2026-06-01 | 2 | 2
PRJ-008 | 2026-07-01 | 10 | 8
PRJ-008 | 2026-08-01 | 22 | 17
PRJ-008 | 2026-09-01 | 36
PRJ-008 | 2026-10-01 | 51
PRJ-008 | 2026-11-01 | 65
PRJ-008 | 2026-12-01 | 78
PRJ-013 | 2026-01-01 | 0 | 0
PRJ-013 | 2026-02-01 | 0 | 0
PRJ-013 | 2026-03-01 | 0 | 0
PRJ-013 | 2026-04-01 | 0 | 0
PRJ-013 | 2026-05-01 | 1 | 0
PRJ-013 | 2026-06-01 | 7 | 6
PRJ-013 | 2026-07-01 | 18 | 16
PRJ-013 | 2026-08-01 | 33 | 29
PRJ-013 | 2026-09-01 | 49
PRJ-013 | 2026-10-01 | 64
PRJ-013 | 2026-11-01 | 76
PRJ-013 | 2026-12-01 | 84
PRJ-019 | 2026-01-01 | 0 | 0
PRJ-019 | 2026-02-01 | 0 | 0
PRJ-019 | 2026-03-01 | 0 | 0
PRJ-019 | 2026-04-01 | 0 | 0
PRJ-019 | 2026-05-01 | 0 | 0
PRJ-019 | 2026-06-01 | 0 | 0
PRJ-019 | 2026-07-01 | 0 | 0
PRJ-019 | 2026-08-01 | 0 | 0
PRJ-019 | 2026-09-01 | 0
PRJ-019 | 2026-10-01 | 0
PRJ-019 | 2026-11-01 | 0
PRJ-019 | 2026-12-01 | 0
PRJ-023 | 2026-01-01 | 0 | 0
PRJ-023 | 2026-02-01 | 0 | 0
PRJ-023 | 2026-03-01 | 0 | 0
PRJ-023 | 2026-04-01 | 0 | 0
PRJ-023 | 2026-05-01 | 0 | 0
PRJ-023 | 2026-06-01 | 0 | 0
PRJ-023 | 2026-07-01 | 0 | 0
PRJ-023 | 2026-08-01 | 17 | 13
PRJ-023 | 2026-09-01 | 50
PRJ-023 | 2026-10-01 | 91
PRJ-023 | 2026-11-01 | 100
PRJ-023 | 2026-12-01 | 100
GLB-004 | 2026-01-01 | 0 | 0
GLB-004 | 2026-02-01 | 0 | 0
GLB-004 | 2026-03-01 | 0 | 0
GLB-004 | 2026-04-01 | 1 | 1
GLB-004 | 2026-05-01 | 6 | 5
GLB-004 | 2026-06-01 | 14 | 12
GLB-004 | 2026-07-01 | 23 | 21
GLB-004 | 2026-08-01 | 33 | 31
GLB-004 | 2026-09-01 | 44
GLB-004 | 2026-10-01 | 52
GLB-004 | 2026-11-01 | 59
GLB-004 | 2026-12-01 | 62
PRJ-001 | 2026-01-01 | 0 | 0
PRJ-001 | 2026-02-01 | 0 | 0
PRJ-001 | 2026-03-01 | 0 | 0
PRJ-001 | 2026-04-01 | 5 | 4
PRJ-001 | 2026-05-01 | 13 | 12
PRJ-001 | 2026-06-01 | 25 | 22
PRJ-001 | 2026-07-01 | 38 | 33
PRJ-001 | 2026-08-01 | 52 | 46
PRJ-001 | 2026-09-01 | 65
PRJ-001 | 2026-10-01 | 74
PRJ-001 | 2026-11-01 | 80
PRJ-001 | 2026-12-01 | 82
PRJ-003 | 2026-01-01 | 6 | 5
PRJ-003 | 2026-02-01 | 12 | 10
PRJ-003 | 2026-03-01 | 18 | 16
PRJ-003 | 2026-04-01 | 27 | 24
PRJ-003 | 2026-05-01 | 35 | 32
PRJ-003 | 2026-06-01 | 44 | 40
PRJ-003 | 2026-07-01 | 52 | 47
PRJ-003 | 2026-08-01 | 59 | 54
PRJ-003 | 2026-09-01 | 65
PRJ-003 | 2026-10-01 | 69
PRJ-003 | 2026-11-01 | 70
PRJ-003 | 2026-12-01 | 70
PRJ-007 | 2026-01-01 | 4 | 3
PRJ-007 | 2026-02-01 | 9 | 7
PRJ-007 | 2026-03-01 | 14 | 12
PRJ-007 | 2026-04-01 | 21 | 18
PRJ-007 | 2026-05-01 | 29 | 24
PRJ-007 | 2026-06-01 | 37 | 31
PRJ-007 | 2026-07-01 | 45 | 38
PRJ-007 | 2026-08-01 | 52 | 44
PRJ-007 | 2026-09-01 | 58
PRJ-007 | 2026-10-01 | 63
PRJ-007 | 2026-11-01 | 67
PRJ-007 | 2026-12-01 | 68
PRJ-010 | 2026-01-01 | 0 | 0
PRJ-010 | 2026-02-01 | 1 | 0
PRJ-010 | 2026-03-01 | 3 | 3
PRJ-010 | 2026-04-01 | 9 | 8
PRJ-010 | 2026-05-01 | 16 | 14
PRJ-010 | 2026-06-01 | 26 | 22
PRJ-010 | 2026-07-01 | 35 | 31
PRJ-010 | 2026-08-01 | 45 | 40
PRJ-010 | 2026-09-01 | 55
PRJ-010 | 2026-10-01 | 64
PRJ-010 | 2026-11-01 | 72
PRJ-010 | 2026-12-01 | 77
PRJ-014 | 2026-01-01 | 14 | 13
PRJ-014 | 2026-02-01 | 21 | 19
PRJ-014 | 2026-03-01 | 27 | 26
PRJ-014 | 2026-04-01 | 35 | 33
PRJ-014 | 2026-05-01 | 43 | 40
PRJ-014 | 2026-06-01 | 50 | 47
PRJ-014 | 2026-07-01 | 56 | 53
PRJ-014 | 2026-08-01 | 61 | 58
PRJ-014 | 2026-09-01 | 65
PRJ-014 | 2026-10-01 | 66
PRJ-014 | 2026-11-01 | 66
PRJ-014 | 2026-12-01 | 66
PRJ-020 | 2026-01-01 | 0 | 0
PRJ-020 | 2026-02-01 | 0 | 0
PRJ-020 | 2026-03-01 | 1 | 0
PRJ-020 | 2026-04-01 | 4 | 4
PRJ-020 | 2026-05-01 | 11 | 9
PRJ-020 | 2026-06-01 | 19 | 17
PRJ-020 | 2026-07-01 | 30 | 26
PRJ-020 | 2026-08-01 | 41 | 35
PRJ-020 | 2026-09-01 | 52
PRJ-020 | 2026-10-01 | 63
PRJ-020 | 2026-11-01 | 73
PRJ-020 | 2026-12-01 | 81
GLB-005 | 2026-01-01 | 0 | 0
GLB-005 | 2026-02-01 | 0 | 0
GLB-005 | 2026-03-01 | 1 | 1
GLB-005 | 2026-04-01 | 6 | 5
GLB-005 | 2026-05-01 | 13 | 12
GLB-005 | 2026-06-01 | 22 | 20
GLB-005 | 2026-07-01 | 33 | 30
GLB-005 | 2026-08-01 | 44 | 40
GLB-005 | 2026-09-01 | 55
GLB-005 | 2026-10-01 | 65
GLB-005 | 2026-11-01 | 73
GLB-005 | 2026-12-01 | 78
PRJ-004 | 2026-01-01 | 39 | 36
PRJ-004 | 2026-02-01 | 46 | 43
PRJ-004 | 2026-03-01 | 53 | 49
PRJ-004 | 2026-04-01 | 59 | 56
PRJ-004 | 2026-05-01 | 65 | 62
PRJ-004 | 2026-06-01 | 71 | 67
PRJ-004 | 2026-07-01 | 75 | 71
PRJ-004 | 2026-08-01 | 79 | 75
PRJ-004 | 2026-09-01 | 81
PRJ-004 | 2026-10-01 | 81
PRJ-004 | 2026-11-01 | 81
PRJ-004 | 2026-12-01 | 81
PRJ-012 | 2026-01-01 | 54 | 56
PRJ-012 | 2026-02-01 | 60 | 63
PRJ-012 | 2026-03-01 | 66 | 69
PRJ-012 | 2026-04-01 | 72 | 75
PRJ-012 | 2026-05-01 | 77 | 80
PRJ-012 | 2026-06-01 | 82 | 85
PRJ-012 | 2026-07-01 | 85 | 88
PRJ-012 | 2026-08-01 | 87 | 90
PRJ-012 | 2026-09-01 | 88
PRJ-012 | 2026-10-01 | 88
PRJ-012 | 2026-11-01 | 88
PRJ-012 | 2026-12-01 | 88
PRJ-016 | 2026-01-01 | 10 | 10
PRJ-016 | 2026-02-01 | 17 | 16
PRJ-016 | 2026-03-01 | 25 | 22
PRJ-016 | 2026-04-01 | 33 | 30
PRJ-016 | 2026-05-01 | 42 | 38
PRJ-016 | 2026-06-01 | 51 | 47
PRJ-016 | 2026-07-01 | 59 | 55
PRJ-016 | 2026-08-01 | 67 | 62
PRJ-016 | 2026-09-01 | 73
PRJ-016 | 2026-10-01 | 78
PRJ-016 | 2026-11-01 | 82
PRJ-016 | 2026-12-01 | 83
PRJ-022 | 2026-01-01 | 28 | 26
PRJ-022 | 2026-02-01 | 36 | 33
PRJ-022 | 2026-03-01 | 43 | 39
PRJ-022 | 2026-04-01 | 50 | 46
PRJ-022 | 2026-05-01 | 57 | 53
PRJ-022 | 2026-06-01 | 64 | 59
PRJ-022 | 2026-07-01 | 69 | 64
PRJ-022 | 2026-08-01 | 74 | 69
PRJ-022 | 2026-09-01 | 78
PRJ-022 | 2026-10-01 | 80
PRJ-022 | 2026-11-01 | 80
PRJ-022 | 2026-12-01 | 80
PRJ-026 | 2026-01-01 | 35 | 33
PRJ-026 | 2026-02-01 | 43 | 41
PRJ-026 | 2026-03-01 | 50 | 48
PRJ-026 | 2026-04-01 | 58 | 55
PRJ-026 | 2026-05-01 | 65 | 62
PRJ-026 | 2026-06-01 | 71 | 68
PRJ-026 | 2026-07-01 | 76 | 73
PRJ-026 | 2026-08-01 | 81 | 78
PRJ-026 | 2026-09-01 | 83
PRJ-026 | 2026-10-01 | 84
PRJ-026 | 2026-11-01 | 84
PRJ-026 | 2026-12-01 | 84